## MOSIP_QueryLog_External
MOSIP - Requirements Change Log
S.No. | Date of Identification | Reference (User Story/Document, Version, Section, REQ ID, Page) | Module | New / De-scoped | Change Description | Logged By | Comments - Shrikant | Version | Approved/Rejected | Approver | Date | CUT Effort (PDs) | Effort (PDs) Incl. of Testing | Comments - On PD(s)
1 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Mode of login to client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint, iris. Morocco FRS: Single factor authentication using either password or OTP Query log review: Multifactor authentication using username + password and/or OTP, fingerprint, iris. Also applies to operator authentication while submitting a registration. | Vivek | Build as per Backlog, Morocco will remove what it does not want, as part of its configuration. | 1 | Approved | Shrikant | 2018-11-15 | 36 | 72 | Need to develop for the face authentication Tables to maintiane the login sequence. Config sync should provide the which sequence order we need to display.
2 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Fingerprint capture during registration: Backlog: In scope Morocco FRS: Not in scope Query log review: In MVP | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | 1 | Approved | Shrikant | 2018-11-15 | 12 | 24 | Configiuration for the FingerPrint enable/disable.
3 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Best finger detection in registration receipt: Backlog: Indicate the finger with best quality score. Morocco FRS: Not in scope. Query log review: Indicate a 1-10 ranking of fingers by quality scores. | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | 1 | Approved | Shrikant | 2018-11-15 | 35 | 70 | Dependent on SDK [To find the finger quality and threshould]
4 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Face photograph validation during registration: Backlog: Build validation for ICAO standards. Morocco FRS: Not in scope Query log review: Build for ICAO plus one other standard. | Vivek | It should be part of MOSIP Scope 1.0 | 1 | Approved | Shrikant | 2018-11-15 | 30 | 60 | Dependent on SDK [To find the face quality and threshould]. Standards has to be identified.
5 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Client administration / registration / configuration: The feature is scoped but not as part of a separate application. | Vivek | All in one application is fine. | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
6 | 2018-09-19 | FRS review of Morocco FRS <Annexure D - Functional Requirement Specification dtd 15062018 [F]> | Registration Client | New | (Placeholder for features not covered above which are present in backlog but not in Morocco FRS) For example - Translation and transliteration, Introducer concept, End of day supervisor approval, Registration correction. | Vivek | Introducer can be version 2, rest all in version 1. Morocco also want EOD etc | 1 | Approved | Shrikant | 2018-11-15 | 36 | 72
7 | 2018-10-22 | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | ID Authentication | De-scoped | 1. MOSIP to have the ability to configure scenarios when individual to be notified (Through a periodic job) to update biometrics: -Child turns 5/15 -Authentication cosistently fails beyond x (configurable) times of being below the defined NFIQ threshold (configurable) Reference from Query Log: Page 42 of the RFP for SI states:"RNP may maintain a threshold for quality of biometrics and in case the quality of captured biometrics does not satisfy the threshold, the RNP may intimate the resident to update their biometrics." Does MOSIP scope include the requirement to intimate a resident to update their biometrics if quality is below threshold? As we understand, this can be triggered if a high NFIQ score is identified during authentication but the authentication fails | Hema | In scope. Can be built in version 2.0 | 2 | Approved | Shrikant | 2018-11-15 |  | 0
8 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Client | New | Mode of login to client, Mode of local duplicate check on client, Mode of officer authentication at end of each registration on client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint - Iris and Face is a new inclusion as requested by GoM/PwC | Resham | It should be part of MOSIP Scope 1.0 | 1 | Approved | Shrikant | 2018-11-15 | 20 | 40 | Dependent on Photo SDk
9 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | CNIE Validation/External Data Enrichment Module: 1. Inclusion of step for external system integration 2. Integration with CNIE, EC and Foreign Registration for exchange of information 3. Module with User Interface for manual validation process | Resham | Interface to access data (for View) and Accept data as an update. To be part of MOSIP 1.0 Only currently. | 1 | Approved | Shrikant | 2018-11-15 | 24 | 48 | Assumptions : RP will expose 2 apis 1. to provide applicant info. 2. receive updated info and incorporate it.
10 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | CNIE Finger Print Authentication: 1. Integration with CNIE for obtaining the fingerprint data (a) in the process of demographic validation check with CNIE and (b) Biometric Update in CNIE 2. Integration of authentication solution with Fingerprint SDK 3. Decryption, Quality Analysis, Extraction and Loading features for fingerprints using the received fingerprint data from CNIE 4. Testing of the above functionalities in the five CSCs | Resham | FP received from CNIE via update interface of MOSIP, to extract minutiae etc. | 1 | Approved | Shrikant | 2018-11-15 | 36 | 72 | Estimation may change after understanding overall scope of the change.
11 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | UIN Generator: • Common NIP generator between EC and RNP • NIP generator outside IDMS • NIP generator with a density of 5% for non-guess ability • Incorporation of NIP logic (refer above) within NIP generator • APIs for integration with EC • Porting of the already generated NIPs • For those children which have been allocated NIPs by EC, the same numbers should get allocated and new numbers should not get allocated • The already generated numbers by EC should not be allocated to anyone else • Testing of integrated generator | Resham | Refer to email Sentby Sanjay on 5th Nov to Mr Nanavati, forwarded to MT on 12/11. Rephrase requirement appropriately. UIN data migration/sync will be handled by SI | 1 | Approved | Shrikant | 2018-11-15 | 48 | 96 | Need more clarification on the requirement. Estimation may change after clarification.
12 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | Face De-duplication: Face ID comparison (Face deduplication) has not been considered in scope of MOSIP - Tech board to advise. - If it is required, MOSIP can provide an interface to send the photo (Maybe in bytes) as per ICAO standards. However, MT will need help from tech board on defining the face specs which can be consumed by GoM to interact with the BSP. GoM/SI will need to ensure the BSP supports face deduplication. | Resham | Face Dedupe part of Mosip 1.0. Approval from Tech board will be taken. Anadi to confirm | 1 | Approved | Shrikant | 2018-11-15 | 30 | 60
13 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | APIs: • MOSIP should provide pull APIs for printing agency > MOSIP should have a queue with PDF files ready for print - TBD with tech team • Printing agency should be able to confirm receipt of pulled information • MOSIP agency should maintain a flag and timestamp of information being pulled by printing agency | Resham | This was part of earlier scope in Scoping phase itself. What has changed. Pls clarify . > To be included in Product Backlog | 1 | Approved | Shrikant | 2018-11-15 | 28 | 56 | Estimation may change after understanding overall scope of the change.
14 |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | New | UIN Update Appointment Scheduling: - Ability to schedule appointments on Resident Services for UIN updates | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
15 |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | New | UIN Update Approval: - Ability to facilitate approval of UIN update requests received through resident service portal | Resham | Part of verison 1. 0. Part of Scoping phase itself | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
16 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Mark applicant as Foreigner/Non-Foreigner: - Marking an individual as foreigner/non-foreigner during registration - Capturing docs/data accordingly | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 10 | 30 | Packet changes/UI/DTO/
17 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Verified/Non-Verified: - Marking an individual's DoB as verified/non-verified | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 5 | 10 | Packet changes/UI/DTO/
18 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Processor | New | Manual Activation/De-activation of UIN: a. Manual Activation of UIN (By admin through backend – EG: xls) b. Manual De-activation of UIN (By admin through backend – EG: xls) c. Manual Re-activation of UIN (By admin through backend – EG: xls) | Resham | Part of Data enhance module. Version 1.0 | 1 | Approved | Shrikant | 2018-11-15 | 20 | 40 | Since the requirement is not detailed the effort may change.
19 | 2018-10-29 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | New | Replace VID: Ability of the UIN holder to invalidate an active VID, on the web portal | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
20 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | resident portal, Dashboards, Reports | New | Digital Signature for Offline UIN Verification: Include digital signature as part of the e-UIN generated, to facilitate offline UIN verification | Resham | Part of Version 1.0 | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
21 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Marking Packets for Deletion: MOSIP should mark registration packets for deletion on successful UIN generation or 45 days, which ever is later. | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 10 | 20 | This is to be implemented for New Reg, Update UIN, Lost UIN functionality.
22 | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | Registration Client | New | Configure Packet Size: Include ability to configure the registration packet size | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 5 | 10 | If the packet size is greater than mentioned what we need to do with the capture data ?
23 | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | New | Retrieve VID: Ability of UIN holder to retrieve all active VIDs on the web portal | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0
24 | 2018-11-14 | Discussion with Anadi | DevOps | New | Infrastructure as Code - IAAC: 1. As per the SOW, we had planned to setup 2 environments – Dev and QA. A new request to have additional infrastructure created and codify the same | Resham | Part of verison 1. 0. | 1 | Approved | Anadi | 2018-11-15 | 30 | 60
25 | 2018-11-14 | MOS-9602 | Registration Processor | New | id Definition Implementation: 1. Registration-processor-core update with new structure of PacketMetaInfo.json 2. packet-validator update with new structure of PacketMetaInfo.json 3. packet-info-storage-service update with new structure of PacketMetaInfo.json | Resham | Part of verison 1. 0. | 1 | Approved | Anadi | 2018-11-15 | 10 | 20 | Implemented in Sprint 5
26 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Pre-registration | New | Booking Appointment: 1. Update UX - Recommend drag and drop approach to book time slots, VD update based on removal of group concept, other changes in VDs | Resham | Drag and drop approach or better should be implemented | 1 |  |  |  |  | 0
27 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | New | Mapping of Machines with Devices at Registration Centre: 1. The mapping of machines with devices seems redundant. Since the machine to device mapping data is not carried in the registration packet and there is no device to machine mapping validation on server side, this requirement is not valid | Resham | The mapping requirement is valid. 1. Data related to Machine mapping with all devices should be a part of the packet 2. The existence of the devices and its respective mapping should be validated on the client and server side | 1 | Approved | Shrikant | 2018-12-06 | 10 | 20 | Existing packet structure to be modified and serial no. validation against device and db.
28 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | New | Un-lock Registration Client Account post un-successful login: 1. Include: Supervisor/Admin’s ability to unlock Registration Officer’s account in case it is locked, due to x incorrect login attempts | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 15 | 30 | UI + API
29 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | New | EoD Process - Reason for Rejection: 1. Apart from the configured reasons for Rejection, consider providing an option “Other” with ability of user to enter free text/comments | Resham | This is not required. This should be driven by master data as defined by the Country. | 1 | Approved | Shrikant | 2018-12-06 | 1 | 3
30 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh - MOS-9749 | ID Authentication | New | Multi-Factor Authentication: 1. In case of multi-factor authentication, MOSIP should respond back with eKYC data based on alternate preferred business rules, as preferred by SI Current implementation sends a positive response only if all configured parameters match Include feasibility for a Country/SI to accommodate business rule to send a positive response if 2 out of 3 factors match, to clear authentication – Without Code change by SI | Resham | To be implemented as per MOS-9749 - As per discussion with Sanjay, we will authenticate by matching all details passed => demo, multiple biometrics. The match will be an “AND” - If there is no specific reason in restricting 2 biometric modalities, MOSIP will allow all three biometric modalities in a single transaction and will do an ‘AND’ | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | This is the current implementation, assuming all authentication types has equal weightage, we will perform AND of all input Auth Types.
31 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Configure preferred Matching Strategy for Authentication: 1. TSP Config to be included – The matching strategy/threshold per TSP should be configurable (EG: Exact vs. partial match per parameter – Name/address) - Mode of Matching Strategy should be configurable by SI | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy for text in v1. Phonetics match should be considered as part of v2 | 1 | Approved | Shrikant | 2018-12-06 | 10 | 20 | Considering only exact match for Demo Auth, both partial and phonetics are to be disabled - needs to be made configurable at country level and validation for this needs to be added
32 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Demographic (Address) Authentication: 1. Algorithm for various address fields should have specific weightage – EG: Postal Code threshold should be 100% vs. address Line 1 could be <60% Current Implementation: No weightage is provided to each field but exact match strategy is adopted 2. Response should also provide a confidence score, based on the weightage logic Current Implementation: No confidence score is provided 3. Align Demographic (address) authentication algorithm with Demographic Dedupe algorithm | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | Will be taken care as part of S.No. 31
33 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Phonetics Match: 1.Include ability to configure preferred matching strategy by means of placing the preferred algorithm in a jar file vs. a code change by SI - Current Implementation: Algorithm is part of the code with limited matching strategies. SI is expected to write code for preferred strategies | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | Will be taken care as part of S.No. 31
34 | 2018-11-26 | Requirements Elicitation Phase | Pre-registration | De-scoped | Login with Username/Password: 1. This is not a high priority requirement and can be moved to v2 | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-06 |  | 0
35 | 2018-11-26 | Requirements Elicitation Phase | Registration Client | De-scoped | Introducer Concept: 1. This is not a high priority requirement and should be moved to v2 | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-06 |  | 0
36 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | RID Correction: 1. This is not a valid requirement and should be de-scoped from MOSIP | Resham | This is not required. | NA | Approved | Shrikant | 2018-12-06 |  | 0
37 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Lost UIN: 1. This is not a valid requirement and should be de-scoped from MOSIP | Resham | This should be implemented | 2 | Approved | Shrikant | 2018-12-18 |  | 0
38 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Quality Check of Individual's Data: 1. Quality Check should not be a manual process 2. It should be automated (Machine Learning based) 3. It should be the first step when the packet is received 4. It should involve verification of: a. Photo - Age check - Gender check - Human face - One face - Liveness detection of photograph b. Document - OCR - Extract data from document (EG: Name, DOB) and match against demographic details provided - Check document authenticity c. Check Biometrics: - Finger quality checks: Real finger, Of the same person | Resham | Automated QC should be implemented as part of v1 - Towards May'18 | 1+ | Approved | Shrikant | 2018-12-06 | 45 | 90 | Photo verification automation and document verification automation
39 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. Multi-model deduplication – MOSIP to give all biometrics to ABIS > Receive scores from ABIS > Derive an overall composite score across modalities by utilizing scores from each modality (dedupe type) > Automate the evaluation of derived result > MOSIP to have a fusion algorithm to derive a composite score 4. Include manual adjudication after biometric dedupe 5. Ability of system to receive scores for face dedupe to derive the composite score (ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe) | Resham | 1. Multi-modality concept should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 55 | 55 | Need more clarification on the requirement. Estimation may change after clarification.
40 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | De-scoped | Deduplication: 1. Implement Multi-ABIS solution 2. Create dummy ABIS 4. Include manual adjudication after biometric dedupe 5. Ability of system to receive scores for face dedupe to derive the composite score (ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe) | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-06 | 60 |  | Since there was no poc on ABIS we need to check abis APIs works, input and output to create dummy abis.
41 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. Create dummy ABIS | Resham | This can be evaluated based on outcome of Cloud ABIS capability | 1 | Approved | Shrikant | 2018-12-06 | 48 |  | Since there was no poc on ABIS we need to check abis APIs works, input and output to create dummy abis.
42 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. Include manual adjudication after biometric dedupe | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-18 | 14 |  | Since manual adjudication has already been implemented so assumption is only change in camel configuration. Estimation may change if scope is more.
43 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. MOSIP to be capable of receiving scores for face dedupe to derive the composite score > ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe | Resham | Support for multimodal ABIS. For GoM this is a single ABIS to which we pass all biometric information. The ABIS will provide the composite score for the dedupe. | 1 | Approved | Ramesh | 2018-12-18 | 30 |  | deriving composite score logic.
| 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. MOSIP to be capable of receiving scores for face dedupe to derive the composite score > ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe | Resham | MOSIP should have the ability to see how good an ABIS is by integrating with alternative ABIS providers to get their scores. Calling ABIS (one or many per mode), composing the score should be separate steps in the process which can be provided alternative implementations. Current implementation (v1) will call one ABIS and the composed score will be the same as the ABIS returned score. | 1+ | Approved | Ramesh | 2018-12-18
| 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. MOSIP to be capable of receiving scores for face dedupe to derive the composite score > ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe | Resham | A reference mechanism to compose our own score from individual scores from mode specific (finger, iris, face,..) ABIS. | 2 | Approved | Ramesh | 2018-12-18
44 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Demographic Deduplication: 1. Inclusion of phonetics match for name in demographic dedupe algorithm - Usage of SoundEx | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 12 | 24 | Change algorithm from lavenstine distance to phonetic and soundex match
45 | 2018-11-23 | Discussion with Vivek Raghavan | ID Authentication | New | Storage of Biometrics as Images: 1. MOSIP should store the actual biometric images instead of minutiae | Resham | MOSIP API for v1 should support storage and auth with minutiae. MOSIP API for v2 should support storage and auth with minutiae and image. | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | Since FMR is only in V1, it was already factored while in V1 estimates, hence no estimates needs to be added for V1
46 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Biometrics for Minors - Workflow: 1. MOSIP should capture biometrics for minors and have a separate workflow around it (Less/different rules as compared to adults) | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-06 |  | 0
47 | 2018-11-23 | Discussion with Vivek Raghavan | resident portal, Dashboards, Reports | New | VID Generation Concept: 1. VID concept should be as per aadhaar guidelines vs. given requirement of multiple active VIDs at a given point a. Aadhaar VID is not consumption based for expiry b. Multiple VIDs can be generated c. No validity to a VID generated d. On generation of new VID, previous one is invalidated e. One VID can be used with multiple TSPs f. MOSIP to implement as per aadhaar principle, as above g. SI can implement as preferred - MOSIP to build hooks for other preferences | Resham | Aadhaar way | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0
48 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | Update UIN: 1. MOSIP should allow to configure which fields can be updated through portal vs. at the registration Centre (Name/DoB/Address/Phone/Email) | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 12 | 24 | UI + API changes. Configuration changes.
49 | 2018-11-23 | Discussion with Vivek Raghavan | resident portal, Dashboards, Reports | New | Lock UIN: 1. MOSIP should allow UIN holder to lock UIN for authentication and further un-lock if required | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0
50 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | User Onboarding - Login using QR Code through Mobile: 1. Usage of QR codes through mobile for login to registration Client | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-18 |  | 0
51 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | User Onboarding - Remote mapping of user to Machine: 1. Admin registers the users. Tfurther the RO should be able to onboard himself without the requirement of a SPVR/Admin as an entry point | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-18 | 20 | 40 | UI + API changes.
52 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | Geo-location Capture using GPS: 1. Usage of phones for GPS vs. GPS on machine | Resham | This should be implemented as it reduces hardware dependency | 1 | Approved | Shrikant | 2018-12-06 | 40 | 80 | Mobile has different OS. Integrate and getting infromation from IOS might become challenges. Need to do the POC on multiple mobile platform [IOS, Android, Black berry, Simbion OS and windows]
53 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Registration Client on Exclusive Devices: 1. Dongle based approach vs. running client on exclusive devices (Linux based) procured for registration only - EG: Chromebook | Resham | This can be implemented based on demand | 2 | Approved | Shrikant | 2018-12-06 |  | 0
54 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Whitelisted Station Concept: 1. This refers to a station that can execute features which other stations cannot do (Update name/DoB beyond the stipulated restriction) 2. This would lead to configurations at station (Registration Centre) level | Resham | This can be implemented as part of Resident Services portal where a Service provider can obtain biometrics of UIN holder, perform biometric auth for specific updates | 2 | Approved | Shrikant | 2018-12-06 |  | 0
55 | 2018-11-28 | Sprint 7 story grroming feedback from Ramesh - 28Nov'18 | Kernel | New | ID Length Change: 1. Update maximum length of Machine ID in DB from 36 to 10 2. Update maximum length of Registration Centre ID in DB from 36 to 10 3. Update maximum length of RID in DB from 28 to 39 4. Please confirm the length for Device ID to be 36 | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 4 | 8
56 | 2018-11-28 | Discussion with Vivek Raghavan | ID Authentication | New | Face Authentication: 1. Face authentication can be moved to a later version of MOSIP and is out of scope for v1 | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | Already estimated as part of V1 Release Plan
57 | 2018-11-28 | Discussion with Vivek Raghavan | Registration Processor | New | Virus Scan: 1. Virus scan should be performed before and after decryption of registration packet, during processing | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-06 | 14 | 28 | need to install clamav in private network VM and minor code changes
58 | 2018-11-28 | Internal requirement evaluation | Kernel | De-scoped | ID Validation Components de-scoped: The following components have been de-scoped as there is no valid use-case: 1. Token ID Validation 2. Static PIN Validation 3. Registration Center ID Validation 4. Machine ID Validation | Resham | This can be implemented based on demand - No requirement identified in v1 | 2 | Approved | Shrikant | 2018-12-06
59 | 2018-11-28 | Requirements Elicitation Discussion with Shrikant_Email dated 14Nov18 on "ID Generation" | Kernel | De-scoped | Static PIN Generation: 1. This has been de-scoped as the Resident is expected to set it up in resident portal | Resham | OK | NA | Approved | Shrikant | 2018-12-06
60 | 2018-12-06 | Query log review with Anadi/Ramesh (JIRA) on 06-Dec-18 | ID Authentication | New | License Key Generation: 1. License key generation to be invoked through admin portal with an approval process > Key to be associated to the TSP ID > TSP should have a mechanism to access the key 2. MOSIP should support multiple license keys per TSP. There will be a separate license key per use case / application with associated policy 3. Once a TSP is authorized they should ideally have a self-service (TSP Portal) mechanism to get their keys, and regenerate them on need basis. In the absence of a Self-Service portal, it should be possible for the admin to generate the key and email it to the TSP. This can be done as part of the approval process, as well as on an ad hoc basis when the key needs to be replaced | Resham | This should be implemented | 1 | Approved | Ramesh | 2018-12-18 | 15 | 30 | Assuming that we will have multiple license keys per TSP, which will be then mapped to multiple allowed Auth types and a separate functionality to generate Licence Keys would be required in Admin Portal
61 | 2018-12-06 | GoM Requirements | Registration Client | New | OCR as part of Document Upload: 1. As per GoM, MOSIP should support quality check of documents during document upload. Current Implementation: MOSIP will perform basic file validations like file size and file format New requirement as per discussions with Shrikant: MOSIP should support OCR as part of quality check of documents during document upload. | Resham | This should be implemented | 1+ | Approved | Shrikant | 2018-12-18 | 30 | 60 | It depends on the SDK provided by the scanner device. We can check for an option to capture the quality of document captured during scanning if SDK provides. Need to do some poc on this area.
62 | 2018-12-06 | GoM Requirements | Pre-registration | New | OCR as part of Document Upload: 1. As per GoM, MOSIP should support quality check of documents during document upload. Current Implementation: MOSIP will perform basic file validations like file size and file format New requirement as per discussions with Shrikant: MOSIP should support OCR as part of quality check of documents during document upload. | Resham | This should be implemented | 1+ | Approved | Shrikant | 2018-12-18
63 | 2018-12-12 | Ancillary process flow reviwe with Shrikant/Ramesh: Refer MoM dated: 12-Dec-18 | Registration Client | New | Packet Upload: a. Online Mode: i. Registration completed and Packet created (With/Without EoD Process) ii. Initiate Sync from Client to send RID details to Server iii. Server to acknowledge iv. On successful response of ack. From Server, Client to mark packet as “Ready for upload” and initiate auto-upload of packet b. Offline Mode/Low Bandwidth Connection: i. Registration completed and Packet created (With/Without EoD Process) ii. Initiate Sync from Client to send RID details to Server - If connection available iii. Server to acknowledge iv. On successful response of ack. from Server, Client to mark packet as “Ready for upload” v. Packets to be extracted to an external hard drive vi. Packets to be manually uploaded to server | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-12 |  | 24 | Statsus Updated to Exported for the exported. FilePath should be a configurable one. Offline only export should work. Serice changes, UI changes. EOD Approval Screen On/Off.
64 | 2018-12-12 | Ancillary process flow reviwe with Shrikant/Ramesh: Refer MoM dated: 12-Dec-18 | Registration Client | New | EoD Process: a. Provide ability to configure if EoD process is required/not (Turn On/Off) | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-12 |  | 4
65 | 2018-12-17 | Sprint 6 Demo Feedback from Ramesh/Shrikant/Krishnan | Registration Client | New | Pre-registration Data Download: 1. In online mode, on input of PRID, system should trigger an additional validation to check if pre-registration data available is the latest/updated data > Fetch latest data > Override existing downloaded data 2. In offline mode, on input of PRID, system to fetch the existing downloaded pre-registration data > Modifications can be made if required (No change) | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-17 |  | 18 | 1. Pre-Reg Sync/Batch Job Changes 2. Multi-lingual changes 3. ID object based strucutre changes
66 | 2018-12-17 | Sprint 6 Demo Feedback from Ramesh/Shrikant/Krishnan | Registration Client | New | Trigger Notification: 1. Provide an option to add additional Mobile numbers/e-mail IDs to trigger pre-registration confirmation notification to additional recipients as required | Resham | This should be implemented | 1 | Approved | Shrikant | 2018-12-18 |  | 16

## Values
Module
Pre-registration
Registration Client
Registration Processor
ID Authentication
Kernel
Admin
resident portal, Dashboards, Reports

## Pivot
Row Labels | Count of S.No. | Sum of Effort (PDs)
DevOps | 1 | 0
ID Authentication | 8 | 30
Kernel | 3 | 0
Pre-registration | 3 | 0
Registration Client | 27 | 0
Registration Processor | 15 | 0
resident portal, Dashboards, Reports | 7 | 0
Grand Total | 64 | 30