## MOSIP_QueryLog_External
MOSIP - Requirements Change Log
S.No. | Date of Identification | Reference (User Story/Document, Version, Section, REQ ID, Page) | Module | Change Description | Logged By | Comments - Shrikant | Version | Approved/Rejected | Owner | Date
1 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Mode of login to client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint, iris. Morocco FRS: Single factor authentication using either password or OTP Query log review: Multifactor authentication using username + password and/or OTP, fingerprint, iris. Also applies to operator authentication while submitting a registration. |  | Build as per Backlog, Morocco will remove what it does not want, as part of its configuration. | 1 | Approved | Shrikant | 2018-11-15
2 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Fingerprint capture during registration: Backlog: In scope Morocco FRS: Not in scope Query log review: In MVP |  | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | 1 | Approved | Shrikant | 2018-11-15
3 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Best finger detection in registration receipt: Backlog: Indicate the finger with best quality score. Morocco FRS: Not in scope. Query log review: Indicate a 1-10 ranking of fingers by quality scores. |  | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | 1 | Approved | Shrikant | 2018-11-15
4 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Face photograph validation during registration: Backlog: Build validation for ICAO standards. Morocco FRS: Not in scope Query log review: Build for ICAO plus one other standard. |  | It should be part of MOSIP Scope 1.0 | 1 | Approved | Shrikant | 2018-11-15
5 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Client administration / registration / configuration: The feature is scoped but not as part of a separate application. |  | All in one application is fine. | 1 | Approved | Shrikant | 2018-11-15
6 | 2018-09-19 | FRS review of Morocco FRS <Annexure D - Functional Requirement Specification dtd 15062018 [F]> | Registration Client | (Placeholder for features not covered above which are present in backlog but not in Morocco FRS) For example - Translation and transliteration, Introducer concept, End of day supervisor approval, Registration correction. |  | Introducer can be version 2, rest all in version 1. Morocco also want EOD etc | 1 | Approved | Shrikant | 2018-11-15
7 | 2018-10-22 | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | ID Authentication | MOSIP to have the ability to configure scenarios when individual to be notified (Through a periodic job) to update biometrics: -Child turns 5/15 -Authentication cosistently fails beyond x (configurable) times of being below the defined NFIQ threshold (configurable) Reference from Query Log: Page 42 of the RFP for SI states:"RNP may maintain a threshold for quality of biometrics and in case the quality of captured biometrics does not satisfy the threshold, the RNP may intimate the resident to update their biometrics." Does MOSIP scope include the requirement to intimate a resident to update their biometrics if quality is below threshold? As we understand, this can be triggered if a high NFIQ score is identified during authentication but the authentication fails |  | In scope. Can be built in version 2.0 | 2 | Approved | Shrikant | 2018-11-15
8 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Client | Mode of login to client, Mode of local duplicate check on client, Mode of officer authentication at end of each registration on client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint - Iris and Face is a new inclusion as requested by GoM/PwC | Resham | It should be part of MOSIP Scope 1.0 | 1 | Approved | Shrikant | 2018-11-15
9 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | CNIE Validation/External Data Enrichment Module: 1. Inclusion of step for external system integration 2. Integration with CNIE, EC and Foreign Registration for exchange of information 3. Module with User Interface for manual validation process | Resham | Interface to access data (for View) and Accept data as an update. To be part of MOSIP 1.0 Only currently. | 1 | Approved | Shrikant | 2018-11-15
10 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | CNIE Finger Print Authentication: 1. Integration with CNIE for obtaining the fingerprint data (a) in the process of demographic validation check with CNIE and (b) Biometric Update in CNIE 2. Integration of authentication solution with Fingerprint SDK 3. Decryption, Quality Analysis, Extraction and Loading features for fingerprints using the received fingerprint data from CNIE 4. Testing of the above functionalities in the five CSCs | Resham | FP received from CNIE via update interface of MOSIP, to extract minutiae etc. | 1 | Approved | Shrikant | 2018-11-15
11 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | UIN Generator: • Common NIP generator between EC and RNP • NIP generator outside IDMS • NIP generator with a density of 5% for non-guess ability • Incorporation of NIP logic (refer above) within NIP generator • APIs for integration with EC • Porting of the already generated NIPs • For those children which have been allocated NIPs by EC, the same numbers should get allocated and new numbers should not get allocated • The already generated numbers by EC should not be allocated to anyone else • Testing of integrated generator | Resham | Refer to email Sentby Sanjay on 5th Nov to Mr Nanavati, forwarded to MT on 12/11. Rephrase requirement appropriately. UIN data migration/sync will be handled by SI | 1 | Approved | Shrikant | 2018-11-15
12 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | Face De-duplication: Face ID comparison (Face deduplication) has not been considered in scope of MOSIP - Tech board to advise. - If it is required, MOSIP can provide an interface to send the photo (Maybe in bytes) as per ICAO standards. However, MT will need help from tech board on defining the face specs which can be consumed by GoM to interact with the BSP. GoM/SI will need to ensure the BSP supports face deduplication. | Resham | Face Dedupe part of Mosip 1.0. Approval from Tech board will be taken. Anadi to confirm | 1 | Approved | Shrikant | 2018-11-15
13 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | APIs: • MOSIP should provide pull APIs for printing agency > MOSIP should have a queue with PDF files ready for print - TBD with tech team • Printing agency should be able to confirm receipt of pulled information • MOSIP agency should maintain a flag and timestamp of information being pulled by printing agency | Resham | This was part of earlier scope in Scoping phase itself. What has changed. Pls clarify . > To be included in PB | 1 | Approved | Shrikant | 2018-11-15
14 |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | UIN Update Appointment Scheduling: - Ability to schedule appointments on Resident Services for UIN updates | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15
15 |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | UIN Update Approval: - Ability to facilitate approval of UIN update requests received through resident service portal | Resham | Part of verison 1. 0. Part of Scoping phase itself | 1 | Approved | Shrikant | 2018-11-15
16 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | Mark applicant as Foreigner/Non-Foreigner: Marking an individual as foreigner/non-foreigner during registration | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15
17 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Processor | Manual Activation/De-activation of UIN: a. Manual Activation of UIN (By admin through backend – EG: xls) b. Manual De-activation of UIN (By admin through backend – EG: xls) c. Manual Re-activation of UIN (By admin through backend – EG: xls) | Resham | Part of Data enhance module. Version 1.0 | 1 | Approved | Shrikant | 2018-11-15
18 | 2018-10-29 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | Replace VID: Ability of the UIN holder to invalidate an active VID, on the web portal | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15
19 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | resident portal, Dashboards, Reports | Digital Signature for Offline UIN Verification: Include digital signature as part of the e-UIN generated, to facilitate offline UIN verification | Resham | Anadi to clarify requirement - As part of Version 1.0 | 1 | Approved | Shrikant | 2018-11-15
20 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Processor | Marking Packets for Deletion: MOSIP should mark registration packets for deletion on successful UIN generation or 45 days, which ever is later. | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15
21 | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | Registration Client | Configure Packet Size: Include ability to configure the registration packet size | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15
22 | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | Retrieve VID: Ability of UIN holder to retrieve all active VIDs on the web portal | Resham | Part of verison 1. 0. | 1 | Approved | Shrikant | 2018-11-15

## Values
Module
Pre-registration
Registration Client
Registration Processor
ID Authentication
Kernel
Admin
resident portal, Dashboards, Reports