## MOSIP_Feature_Roadmap
MOSIP - Feature Roadmap
S.No. | JIRA ID | Date of Identification | Reference (User Story/Document, Version, Section, REQ ID, Page) | Module | New / De-scoped | Change Description | Logged By | Comments - Shrikant | Comments - Anadi | Decision - 19Feb'19 | Version | Approved/Rejected | Approver | Date | CUT Effort (PDs) | Effort (PDs) Incl. of Testing | Estimated | Status | Sprint | Comments - On PD(s)
1 | MOS-12185 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Mode of login to client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint, iris. Morocco FRS: Single factor authentication using either password or OTP Query log review: Multifactor authentication using username + password and/or OTP, fingerprint, iris. Also applies to operator authentication while submitting a registration. | Vivek | Build as per Backlog, Morocco will remove what it does not want, as part of its configuration. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Config perspective, the parameter will not be marked and only GoM required modes of login should be the primary focus. If the config is marked, then MOSIP should respond with "Feature not available. Scope the other peices (Other modes) in v1+. | Multi-factor auth to be developed as part of v1+ MOSIP_Platform. | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 36 | 54 | Yes |  |  | Device + SDK required for actual bio- implementation. 11/2/19: For GoM_v1.0, we will provide login with UN/PW and OTP only. Biometric based login will not be provided in this version For MOSIP_Platform_v1+, we will provide biometric based login
2 | MOS-16040 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Mode of login to client: Stubbed Implementation Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint, iris. Morocco FRS: Single factor authentication using either password or OTP Query log review: Multifactor authentication using username + password and/or OTP, fingerprint, iris. Also applies to operator authentication while submitting a registration. | Vivek | Build as per Backlog, Morocco will remove what it does not want, as part of its configuration. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Config perspective, the parameter will not be marked and only GoM required modes of login should be the primary focus. If the config is marked, then MOSIP should respond with "Feature not available". Scope the other peices (Other modes) in v1+. | Go as per Anadi's comments for scope of v1-GoM. Multi-factor auth to be developed as part of v1+ MOSIP_Platform. | 1 | Approved | Shrikant | 2018-11-15 | 4 | 6 | NA |  |  | Multifactor authentication has already been implemented with Stubbed Implementation implementation. If bio-metric needs to be excluded then it is already completed.
3 | MOS-12186 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Fingerprint capture during registration: Backlog: In scope Morocco FRS: Not in scope Query log review: In MVP | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Scope the other peices in v1+. My problem is with effort estimate, why so much? | In scope of Version 1 - GoM, as originally planned. Next country is round the corner, FP is an important and simple biometric. This should be configurable as required by the Country. | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 12 | 18 | Yes |  |  | Actual Device + SDK required to implement this.
4 | MOS-16024 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Fingerprint capture during registration: With Stubbed Implementation for FP Backlog: In scope Morocco FRS: Not in scope Query log review: In MVP | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Scope the other peices in v1+. My problem is with effort estimate, why so much? | NA as functionality to be provided as part of v1 | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 10 | 15 | NA |  |  | Already implemented with Stubbed Implementation data for FP. Additional changes required to support the enable / disable of this feature. [capture, exception, preview, ack page changes]
5 | MOS-12187 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Best finger detection in registration receipt: Backlog: Indicate the finger with best quality score. Morocco FRS: Not in scope. Query log review: Indicate a 1-10 ranking of fingers by quality scores. | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Scope the other peices in v1+. My problem is with effort estimate, why so much? | This can be moved to 1+ | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 35 | 52.5 | Yes |  |  | Dependent on SDK [To find the finger quality and threshold]
6 | MOS-16016 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Best finger detection in registration receipt: With Stubbed Implementation for FP quality Backlog: Indicate the finger with best quality score. Morocco FRS: Not in scope. Query log review: Indicate a 1-10 ranking of fingers by quality scores. | Vivek | In scope of Version 1.0 as originally planned. Next country is round the corner, FP is a important and simple biometric. | <22Jan19> Prioritize GoM req with stubbed config/modularity in v1. Scope the other peices in v1+. My problem is with effort estimate, why so much? | Stubbed implementation with functionality (Best Finger detected) to be part of v1-GoM. Depend on a random generator for FP quality and remove dependency on SDK. - Implementation approach and efforts TBD between Karthik & Anadi | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 2 | 3 | Yes |  |  | Stubbed data fp quality.
7 | MOS-12188 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Face photograph validation during registration: Backlog: Build validation for ICAO standards. Morocco FRS: Not in scope Query log review: Build for ICAO plus one other standard. | Vivek | It should be part of MOSIP Scope 1.0 |  | This can be moved to 1+ with plug-in of SDK | 1+(earlier V1) | Approved | Shrikant | 2018-11-15 | 30 | 45 | Yes |  |  | Dependent on SDK [To find the face quality and threshold]. Standards have to be identified. 11/2/19:Retain as part of GoM_v1.0 with basic validations implemented by MOSIP: IMG Size validation Compliance with ICAO standards will be moved to MOSIP_Platform_v1+
8 | MOS-16008 | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | New | Face photograph validation during registration: With Stubbed data for ICAO flag Backlog: Build validation for ICAO standards. Morocco FRS: Not in scope Query log review: Build for ICAO plus one other standard. | Vivek | It should be part of MOSIP Scope 1.0 |  | As part of v1, MOSIP should provide an interface to pass the photo and receive response. SDK can be plugged in when made available. Estimates to be re-visited. | 1 | Approved | Shrikant | 2018-11-15 | 1 | 1.5 | Yes |  |  | Stubbed data for ICAO flag.
9 |  | 2018-09-19 | Query log review on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | De-scoped | Client administration / registration / configuration: The feature is scoped but not as part of a separate application. | Vivek | All in one application is fine. |  |  | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0 | NA
10 |  | 2018-09-19 | FRS review of Morocco FRS <Annexure D - Functional Requirement Specification dtd 15062018 [F]> | Registration Client | New | Not a CR,but these are baseline requirements. (Placeholder for features not covered above which are present in backlog but not in Morocco FRS) For example - Translation and transliteration, Introducer concept, End of day supervisor approval, Registration correction. | Vivek | Introducer can be version 2, rest all in version 1. Morocco also want EOD etc |  | NA - Refer Comments <Column U> | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0 | Yes |  |  | 11/2/19:There is no CR here. EOD approval is already implemented. Translation and transliteration are scheduled for Sprint 9 and 10. Introducer is not needed for Morocco.  Translation - Done  Transliteration: MOSIP will provide an interface to facilitate transliteration. Transliteration with libraries should be handled by SI - To be checked with Pre-registration team  Introducer Concept – Move to MOSIP_Platform_v1+  EoD Approval Process – Done  Registration Correction – De-scoped from MOSIP_Platform_v1+
11 | MOS-13190 | 2018-10-22 | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | ID Authentication | De-scoped | 1. MOSIP to have the ability to configure scenarios when individual to be notified (Through a periodic job) to update biometrics: -Child turns 5/15 -Authentication cosistently fails beyond x (configurable) times of being below the defined NFIQ threshold (configurable) Reference from Query Log: Page 42 of the RFP for SI states:"RNP may maintain a threshold for quality of biometrics and in case the quality of captured biometrics does not satisfy the threshold, the RNP may intimate the resident to update their biometrics." Does MOSIP scope include the requirement to intimate a resident to update their biometrics if quality is below threshold? As we understand, this can be triggered if a high NFIQ score is identified during authentication but the authentication fails | Hema | In scope. Can be built in version 2.0 |  |  | 2 | Approved | Shrikant | 2018-11-15 | NA
12 | MOS-12192 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Client | New | 1.Local duplicate check on client to include iris and face 2. Mode of officer authentication at end of each registration on client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint - Iris and Face is a new inclusion as requested by GoM/PwC | Resham | It should be part of MOSIP Scope 1.0 |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-11-15 | 20 | 30 | Yes |  |  | Dependent on IRIS and Photo SDK and device required for Face and IRIS biometric auth. No Stubbed Implementation implementation, as actual implementation is required for GoM.
14 | MOS-13149 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | CNIE Validation/External Data Enrichment Module: 1. Inclusion of step for external system integration 2. Integration with CNIE, EC and Foreign Registration for exchange of information 3. Module with User Interface for manual validation process Refer the email of the GoM call - Minutes | Resham | Interface to access data (for View) and Accept data as an update. To be part of MOSIP 1.0 Only currently. |  |  | 1 | Approved | Shrikant | 2018-11-15 | 24 | 36 | Yes | Dev yet to start | Sprint 9 | We need API specs to integrate with CNIE. We need a Process Flow of the entire CNIE Process. Clarity in requirement is needed by Sprint 7, will be taken up in Sprint 9.
15 | MOS-13150 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | CNIE Finger Print Authentication: 1. Integration with CNIE for obtaining the fingerprint data (a) in the process of demographic validation check with CNIE and (b) Biometric Update in CNIE 2. Integration of authentication solution with Fingerprint SDK 3. Decryption, Quality Analysis, Extraction and Loading features for fingerprints using the received fingerprint data from CNIE and store in ID repository 4. Testing of the above functionalities in the five CSCs(service center) | Resham | FP received from CNIE via update interface of MOSIP, to extract minutiae etc. |  |  | 1 | Approved | Shrikant | 2018-11-15 | 36 | 54 | Yes | Dev yet to start | Sprint 9 | We need API specs to integrate with CNIE. We need a Process Flow of the entire CNIE Process. Clarity in requirement is needed by Sprint 7, will be taken up in Sprint 9.
16 | MOS-13151 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | UIN Generator: • Common NIP generator between EC and RNP • NIP generator outside IDMS • NIP generator with a density of 5% for non-guess ability • Incorporation of NIP logic (refer above) within NIP generator • APIs for integration with EC • Porting of the already generated NIPs • For those children which have been allocated NIPs by EC, the same numbers should get allocated and new numbers should not get allocated • The already generated numbers by EC should not be allocated to anyone else • Testing of integrated generator | Resham | Refer to email Sentby Sanjay on 5th Nov to Mr Nanavati, forwarded to MT on 12/11. Rephrase requirement appropriately. UIN data migration/sync will be handled by SI |  |  | 1 | Approved | Shrikant | 2018-11-15 | 48 | 72 | Yes | Dev yet to start | Sprint 10 | Process flow diagram on how EC integrates with MOSIP. Clarity in requirement is needed by Sprint 7
17 |  | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | Face De-duplication: Face ID comparison (Face deduplication) has not been considered in scope of MOSIP - Tech board to advise. - If it is required, MOSIP can provide an interface to send the photo (Maybe in bytes) as per ICAO standards. However, MT will need help from tech board on defining the face specs which can be consumed by GoM to interact with the BSP. GoM/SI will need to ensure the BSP supports face deduplication. | Resham | Face Dedupe part of Mosip 1.0. Approval from Tech board will be taken. Anadi to confirm |  |  | 1 | Approved | Shrikant | 2018-11-15 | 0 | 0 | NA | Dev Not Needed Part of Dummy ABIS | NA | Developing a mock ABIS which will do de-dupe, Integration will be conducted once GoM provides its ABIS.
18 | MOS-1071 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | New | APIs: • MOSIP should provide pull APIs for printing agency > MOSIP should have a queue with PDF files ready for print - TBD with tech team • Printing agency should be able to confirm receipt of pulled information • MOSIP agency should maintain a flag and timestamp of information being pulled by printing agency | Resham | This was part of earlier scope in Scoping phase itself. What has changed. Pls clarify . > To be included in Product Backlog |  |  | 1 | Approved | Shrikant | 2018-11-15 | 10 | 15 | Yes | Dev yet to start | Sprint 8 | NA
19 |  |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | New | UIN Update Appointment Scheduling: - Ability to schedule appointments on Resident Services for UIN updates | Resham | Part of verison 1. 0. |  |  | 1 | Approved | Shrikant | 2018-11-15 |  | 0
20 |  |  | Discussion with Shrikant_Query Log Addressal | resident portal, Dashboards, Reports | New | UIN Update Approval: - Ability to facilitate approval of UIN update requests received through resident service portal | Resham | Part of verison 1. 0. Part of Scoping phase itself |  |  | 1 | Approved | Shrikant | 2018-11-15 |  | 0
21 | MOS-12193 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Mark applicant as Foreigner/Non-Foreigner: - Marking an individual as foreigner/non-foreigner during registration - Capturing docs/data accordingly | Resham | Part of verison 1. 0. |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-11-15 | 10 | 15 | Yes |  |  | Packet changes/UI/DTO/ document category changes.
22 |  | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Verified/Non-Verified: - Marking an individual's DoB as verified/non-verified | Resham | Part of verison 1. 0. |  | This can be moved to 1+ | 1+ | Approved | Shrikant | 2018-11-15 | 4 | 6 | Yes |  |  | Packet changes/UI/DTO/ > De-scoped as it is a non-GoM requirement
23 | MOS-1086 MOS-1087 | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Processor | New | Manual Activation/De-activation of UIN: a. Manual Activation of UIN (By admin through backend – EG: xls) b. Manual De-activation of UIN (By admin through backend – EG: xls) c. Manual Re-activation of UIN (By admin through backend – EG: xls) | Resham | Part of Data enhance module. Version 1.0 |  |  | 1 | Approved | Shrikant | 2018-11-15 | 20 | 30 | Yes | Dev yet to start | Sprint 8 | Since the requirement is not detailed the effort may change.
24 |  | 2018-10-29 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | New | Replace VID: Ability of the UIN holder to invalidate an active VID, on the web portal | Resham | Part of verison 1. 0. |  |  | 1 | Approved | Shrikant | 2018-11-15 |  | 0
25 |  | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | resident portal, Dashboards, Reports | New | Digital Signature for Offline UIN Verification: Include digital signature as part of the e-UIN generated, to facilitate offline UIN verification | Resham | Part of Version 1.0 |  |  | 1 | Approved | Shrikant | 2018-11-15 |  | 0
26 |  | 2018-10-29 | Response to GoM old PB Document: <RE: Observations on MOSIP Technology Documents - Response to GoM/PwC Queries> Mail: Dtd 29-Oct-18 (MT to Shrikant) | Registration Client | New | Marking Packets for Deletion: MOSIP should mark registration packets for deletion on successful UIN generation or 45 days, which ever is later. | Resham | Part of verison 1. 0. |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-11-15 | 10 | 15 | Yes |  |  | This is to be implemented for New Reg, Update UIN, Lost UIN functionality.
27 |  | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | Registration Client | New | Configure Packet Size: Include ability to configure the registration packet size | Resham | Part of verison 1. 0. | [Ramesh, 17/1/19] Any check done on the client that can avoid a server rejection is helpful. This is optional on the client. | To be provided in v1 | 1 | Approved | Shrikant | 2018-11-15 | 5 | 7.5 | Yes |  |  | configuration changes.
28 |  | 2018-11-14 | Discussion with Anadi on Consolidated list of Configs and Process workflow that can be configured Mail: Dtd 14-Nov-18 (MT to Anadi) | resident portal, Dashboards, Reports | New | Retrieve VID: Ability of UIN holder to retrieve all active VIDs on the web portal | Resham | Part of verison 1. 0. |  |  | 1 | Approved | Shrikant | 2018-11-15 |  | 0
29 |  | 2018-11-14 | Discussion with Anadi | DevOps | New | Infrastructure as Code - IAAC: 1. As per the SOW, we had planned to setup 2 environments – Dev and QA. A new request to have additional infrastructure created and codify the same | Resham | Part of verison 1. 0. | <22Jan19> Infra as code is not a change request, it was always a part of design as K8. Refer my email on the subject. Shravan to explain. |  | 1 | Approved | Anadi | 2018-11-15 | 30 | 45 | Yes
30 | MOS-9602 | 2018-11-14 | MOS-9602 | Registration Processor | New | id Definition Implementation: 1. Registration-processor-core update with new structure of PacketMetaInfo.json 2. packet-validator update with new structure of PacketMetaInfo.json 3. packet-info-storage-service update with new structure of PacketMetaInfo.json | Resham | Part of verison 1. 0. |  |  | 1 | Approved | Anadi | 2018-11-15 | 20 | 30 | Yes | Dev Complete | Sprint 5 | Implemented in Sprint 5
31 | NA | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Pre-registration | New | Booking Appointment: 1. Update UX - Recommend drag and drop approach to book time slots, VD update based on removal of group concept, other changes in VDs | Resham | Drag and drop approach or better should be implemented | <22Jan19> OK |  | 1 | Approved | Shrikant | 2018-12-06 | 6 | 9 | Yes
32 |  | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | De-scoped | Mapping of Machines with Devices at Registration Centre: 1. The mapping of machines with devices seems redundant. Since the machine to device mapping data is not carried in the registration packet and there is no device to machine mapping validation on server side, this requirement is not valid 12/2/19:This has been descoped | Resham | The mapping requirement is valid. 1. Data related to Machine mapping with all devices should be a part of the packet 2. The existence of the devices and its respective mapping should be validated on the client and server side | [Ramesh, 17/1/19] The operator is onboarded on to the instance of the registration client whether it is on a dongle or directly on a machine. Any biometric device or peripheral associated with the registration center can be used. |  | 1 | Approved | Shrikant | 2018-12-06 | 10 | 15 | Yes |  |  | Existing packet structure to be modified and serial no. validation against device and db.
33 | MOS-12199 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | New | Un-lock Registration Client Account post un-successful login: 1. Include: Supervisor/Admin’s ability to unlock Registration Officer’s account in case it is locked, due to x incorrect login attempts | Resham | This should be implemented | [Ramesh, 17/1/19] Is this needed for Morocco? If not let us park this. If needed, this is a typical area of customization for the SI to do, we should have default validation routines written that the SI can replace. | This can be moved to v2. In v1 - the account freeze period and number of tries should be developed and configurable. Include "Forget Password" feature as part of v1. | 2(Earlier V1) | Approved | Shrikant | 2018-12-06 | 15 | 22.5 | Yes |  |  | UI + API
34 |  | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | Registration Client | New | EoD Process - Reason for Rejection: 1. Apart from the configured reasons for Rejection, consider providing an option “Other” with ability of user to enter free text/comments Other option is available,but entering free text is descoped | Resham | This is not required. This should be driven by master data as defined by the Country. |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | Yes
35 | MOS-13162 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh - MOS-9749 | ID Authentication | New | Multi-Factor Authentication: 1. In case of multi-factor authentication, MOSIP should respond back with eKYC data based on alternate preferred business rules, as preferred by SI Current implementation sends a positive response only if all configured parameters match Include feasibility for a Country/SI to accommodate business rule to send a positive response if 2 out of 3 factors match, to clear authentication – Without Code change by SI | Resham | To be implemented as per MOS-9749 - As per discussion with Sanjay, we will authenticate by matching all details passed => demo, multiple biometrics. The match will be an “AND” - If there is no specific reason in restricting 2 biometric modalities, MOSIP will allow all three biometric modalities in a single transaction and will do an ‘AND’ | <22Jan19> Discuss Change Desc with Ramesh, Sanjays inputs look good. |  | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA | NA | NA | This is the current implementation, assuming all authentication types has equal weightage, we will perform AND of all input Auth Types.
36 | MOS-13162 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Configure preferred Matching Strategy for Authentication: 1. TSP Config to be included – The matching strategy/threshold per TSP should be configurable (EG: Exact vs. partial match per parameter – Name/address) - Mode of Matching Strategy should be configurable by SI | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy for text in v1. Phonetics match should be considered as part of v2 | <22Jan19> OK. Go as per Sanjay's inputs. Correct the change description. Above threshold match for biometric and exact match for demographic data. |  | 1 | Approved | Shrikant | 2018-12-06 | 10 | 15 | Yes | Dev to start | FIT 3 | Considering only exact match for Demo Auth, both partial and phonetics are to be disabled and only validations and configurations for exact match will be added
37 | MOS-13162 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Demographic (Address) Authentication: 1. Algorithm for various address fields should have specific weightage – EG: Postal Code threshold should be 100% vs. address Line 1 could be <60% Current Implementation: No weightage is provided to each field but exact match strategy is adopted 2. Response should also provide a confidence score, based on the weightage logic Current Implementation: No confidence score is provided 3. Align Demographic (address) authentication algorithm with Demographic Dedupe algorithm | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy | <22Jan19> As discussed with Sanjay, there is no change request. Please take it off the list. |  | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA | NA | NA | Will be taken care as part of S.No. 33
38 | MOS-13162 | 2018-11-26 | Sprint 5 Demo Feedback from Ramesh | ID Authentication | New | Phonetics Match: 1.Include ability to configure preferred matching strategy by means of placing the preferred algorithm in a jar file vs. a code change by SI - Current Implementation: Algorithm is part of the code with limited matching strategies. SI is expected to write code for preferred strategies | Resham | As concluded with Sanjay, MOSIP should consider only exact match strategy | <22Jan19> As discussed with Sanjay, there is no change request, exact match is the limited match. Please take it off the list. |  | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA | NA | NA | Will be taken care as part of S.No. 33
39 | MOS-790 | 2018-11-26 | Requirements Elicitation Phase | Pre-registration | De-scoped | Login with Username/Password: 1. This is not a high priority requirement and can be moved to v2 | Resham | This can be implemented based on demand | <22Jan19> OK |  | 2 | Approved | Shrikant | 2018-12-06 |  | 0
40 |  | 2018-11-26 | Requirements Elicitation Phase | Registration Client | New | 12/2-Karthik to give estimates as moved from descoped to new Introducer Concept: 1. This is not a high priority requirement and should be moved to v2 | Resham | This can be implemented based on demand |  | This can be moved to v1+ and implemented based on demand. | 1+(Earlier V2) | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA
41 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | RID Correction: 1. This is not a valid requirement and should be de-scoped from MOSIP | Resham | This is not required. |  |  | NA | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA
42 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | 12/2:Needs clarity Lost UIN: 1. This is not a valid requirement and should be de-scoped from MOSIP | Resham | This should be implemented |  | This can be moved to v2 and implemented based on demand. | 2 | Approved | Shrikant | 2018-12-18 | 0 | 0 | NA
43 | MOS-1082 MOS-8460 MOS-1081 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Quality Check of Individual's Data: 1. Quality Check should not be a manual process 2. It should be automated (Machine Learning based) 3. It should be the first step when the packet is received 4. It should involve verification of: a. Photo - Age check - Gender check - Human face - One face - Liveness detection of photograph b. Document - OCR - Extract data from document (EG: Name, DOB) and match against demographic details provided - Check document authenticity c. Check Biometrics: - Finger quality checks: Real finger, Of the same person | Resham | Automated QC should be implemented as part of v1 - Towards May'18 |  |  | 1+ | Approved | Shrikant | 2018-12-06 | 60 | 90 | Yes | Dev yet to start |  | Need clarity on requirements hence we have High Estimates
44 | MOS-1097 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | De-scoped | Deduplication: 1. Implement Multi-ABIS solution 2. Create dummy ABIS 4. Include manual adjudication after biometric dedupe 5. Ability of system to receive scores for face dedupe to derive the composite score (ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe) | Resham | This can be implemented based on demand |  |  | 2 | Approved | Shrikant | 2018-12-06 | 60 | 90 | Yes |  |  | Clarity and Design of Multi-ABIS is not Clear. Hence, we have high estimates
45 | MOS-11897 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. Create dummy ABIS | Resham | This can be evaluated based on outcome of Cloud ABIS capability |  |  | 1 | Approved | Shrikant | 2018-12-06 | 18 | 27 | Yes | Dev in progress | Sprint 7 | We are Developing a mock ABIS which will do de-dupe, But Integration will be conducted once GoM provides its ABIS.
46 | MOS-16105 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. Include manual adjudication after demographic dedupe | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-18 | 20 | 30 | Yes | We will make Manual Verification Stage Pluggable | NA | We will Provide a Hook for Integration. The below will require a code change to be carried out by the SI i. Add the Country's Manual Verification Layer and ii. Change in Camel Configurations to Add the New Verticel
47 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Deduplication: 1. MOSIP to be capable of receiving scores for face dedupe to derive the composite score > ABIS to perform face dedupe on packets identified as duplicates post demo/biometric dedupe | Resham | A reference mechanism to compose our own score from individual scores from mode specific (finger, iris, face,..) ABIS. |  |  | 2 | Approved | Ramesh | 2018-12-18 |  | 0
48 | MOS-13137 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Processor | New | Demographic Deduplication: 1. Inclusion of phonetics match for name in demographic dedupe algorithm - Usage of SoundEx | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-06 | 5 | 7.5 | Yes | Code to be removed | Sprint8 | As per discussion with Sanjay this is not required. We need to Undo Some Changes as it was Implemented in Sprint 6.
49 | MOS-12165 | 2018-11-23 | Discussion with Vivek Raghavan | ID Authentication | New | Storage of Biometrics as Images: 1. MOSIP should store the actual biometric images instead of minutiae | Resham | MOSIP API for v1 should support storage and auth with minutiae. MOSIP API for v2 should support storage and auth with minutiae and image. | <22Jan19> Biometric image is for v1+. |  | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA | NA | NA | Since FMR is only in V1, it was already factored while in V1 estimates, hence no estimates needs to be added for V1
50 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Biometrics for Minors - Workflow: 1. MOSIP should capture biometrics for minors and have a separate workflow around it (Less/different rules as compared to adults) | Resham | This can be implemented based on demand |  |  | 2 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA
51 |  | 2018-11-23 | Discussion with Vivek Raghavan | resident portal, Dashboards, Reports | New | VID Generation Concept: 1. VID concept should be as per aadhaar guidelines vs. given requirement of multiple active VIDs at a given point a. Aadhaar VID is not consumption based for expiry b. Multiple VIDs can be generated c. No validity to a VID generated d. On generation of new VID, previous one is invalidated e. One VID can be used with multiple TSPs f. MOSIP to implement as per aadhaar principle, as above g. SI can implement as preferred - MOSIP to build hooks for other preferences | Resham | Aadhaar way |  |  | 1 | Approved | Shrikant | 2018-12-06 |  | 0
52 | MOS-12984 | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | Update UIN: 1. MOSIP should allow to configure which fields can be updated through portal vs. at the registration Centre (Name/DoB/Address/Phone/Email) | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-06 | 12 | 18 | Yes |  |  | UI + API changes. Configuration changes.
53 |  | 2018-11-23 | Discussion with Vivek Raghavan | resident portal, Dashboards, Reports | New | Lock UIN: 1. MOSIP should allow UIN holder to lock UIN for authentication and further un-lock if required | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-06 |  | 0
54 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | User Onboarding - Login using QR Code through Mobile: 1. Usage of QR codes through mobile for login to registration Client | Resham | This can be implemented based on demand |  |  | 2 | Approved | Shrikant | 2018-12-18 | 0 | 0 | NA
55 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | Completed already in MOS 1206 and MOS 1330 User Onboarding - Remote mapping of user to Machine: 1. Admin registers the users. Tfurther the RO should be able to onboard himself without the requirement of a SPVR/Admin as an entry point | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-18 | 0 | 0 | Yes |  |  | UI + API changes. Stubbed implementation
55 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | User Onboarding - Remote mapping of user to Machine: 1. Admin registers the users. Further the RO should be able to onboard himself without the requirement of a SPVR/Admin as an entry point | Resham | This should be implemented |  | To be provided in v1 | 1+ | Approved | Shrikant | 2018-12-18 | 20 | 30 | Yes |  |  | UI + API changes.
56 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | New | Geo-location Capture using GPS: 1. Usage of phones for GPS vs. GPS on machine | Resham | This should be implemented as it reduces hardware dependency |  | This can be moved to v2 and implemented based on demand. | 1+(Earlier V1) | Approved | Shrikant | 2018-12-06 | 40 | 60 | Yes |  |  | Mobile has different OS. Integrate and getting infromation from IOS might become challenges. Need to do the POC on multiple mobile platform [IOS, Android, Black berry, Simbion OS and windows]. Implementation Approach to be finalized. Highlevel estimation provided.
57 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Registration Client on Exclusive Devices: 1. Dongle based approach vs. running client on exclusive devices (Linux based) procured for registration only - EG: Chromebook | Resham | This can be implemented based on demand |  |  | 2 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA
58 |  | 2018-11-23 | Discussion with Vivek Raghavan | Registration Client | De-scoped | Whitelisted Station Concept: 1. This refers to a station that can execute features which other stations cannot do (Update name/DoB beyond the stipulated restriction) 2. This would lead to configurations at station (Registration Centre) level | Resham | This can be implemented as part of Resident Services portal where a Service provider can obtain biometrics of UIN holder, perform biometric auth for specific updates |  |  | 2 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA
59 | MOS-9712 | 2018-11-28 | Sprint 7 story grroming feedback from Ramesh - 28Nov'18 | Kernel | New | ID Length Change: 1. Update maximum length of Machine ID in DB from 36 to 10 2. Update maximum length of Registration Centre ID in DB from 36 to 10 3. Update maximum length of RID in DB from 28 to 39 4. Please confirm the length for Device ID to be 36 | Resham | This should be implemented | <22Jan19> small time changes. Include in v1. 12 days of PD needed for these! I need justification for estimate. |  | 1 | Approved | Shrikant | 2018-12-06 | 4 | 5 | Yes
60 | MOS-1155 | 2018-11-28 | Discussion with Vivek Raghavan | ID Authentication | New | Face Authentication: 1. Face authentication can be moved to a later version of MOSIP and is out of scope for v1 | Resham | This should be implemented | <22Jan19> If face is in scope of GoM keep it, else for v1+ |  | 1 | Approved | Shrikant | 2018-12-06 | 0 | 0 | NA | NA | NA | Already estimated as part of V1 Release Plan
61 | MOS-11855 | 2018-11-28 | Discussion with Vivek Raghavan | Registration Processor | New | Virus Scan: 1. Virus scan should be performed before and after decryption of registration packet, during processing | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-06 | 20 | 30 | Yes | Dev Complete | FIT-2 | Need to install clamav in private network VM and minor code changes. There is a Change in the Process Flow and the same has been updated in the Process Flow Diagram.
62 | NA | 2018-11-28 | Internal requirement evaluation | Kernel | De-scoped | ID Validation Components de-scoped: The following components have been de-scoped as there is no valid use-case: 1. Token ID Validation 2. Static PIN Validation 3. Registration Center ID Validation 4. Machine ID Validation | Resham | This can be implemented based on demand - No requirement identified in v1 | <22Jan19> OK |  | 2 | Approved | Shrikant | 2018-12-06
63 | NA | 2018-11-28 | Requirements Elicitation Discussion with Shrikant_Email dated 14Nov18 on "ID Generation" | Kernel | De-scoped | Static PIN Generation: 1. This has been de-scoped as the Resident is expected to set it up in resident portal | Resham | OK | <22Jan19> OK |  | NA | Approved | Shrikant | 2018-12-06
64 | MOS-13156 | 2018-12-06 | Query log review with Anadi/Ramesh (JIRA) on 06-Dec-18 | ID Authentication | New | License Key Generation: 1. License key generation to be invoked through admin portal with an approval process > Key to be associated to the TSP ID > TSP should have a mechanism to access the key 2. MOSIP should support multiple license keys per TSP. There will be a separate license key per use case / application with associated policy 3. Once a TSP is authorized they should ideally have a self-service (TSP Portal) mechanism to get their keys, and regenerate them on need basis. In the absence of a Self-Service portal, it should be possible for the admin to generate the key and email it to the TSP. This can be done as part of the approval process, as well as on an ad hoc basis when the key needs to be replaced | Resham | This should be implemented | <22Jan19> Its an essential part of eKYC security. Should be implemented for v1. Need design and effort estimate. |  | 1 | Approved | Ramesh | 2018-12-18 | 20 | 20 | Yes | Dev to Start | Sprint 9 | Assuming that we will have multiple license keys per TSP, which will be then mapped to multiple allowed Auth types, we will have to build generate and validate functionalities for license keys and mapping them as above. Separate UI to generate Licence Keys, map them to a TSP and then map auth types to a license key would be required in Admin Portal, which is not factored in this estimates. <20/02/2019> Based on latest inputs on MISP user, we have to map only one license key mapped to MISP and validate their expiry. Hence, estimates have been revised.
65 | MOS-12176 | 2018-12-06 | GoM Requirements | Registration Client | New | OCR as part of Document Upload: 1. As per GoM, MOSIP should support quality check of documents during document upload. Current Implementation: MOSIP will perform basic file validations like file size and file format New requirement as per discussions with Shrikant: MOSIP should support OCR as part of quality check of documents during document upload. | Resham | This should be implemented |  | This can be moved to v1+ | 1+ | Approved | Shrikant | 2018-12-18 | 30 | 45 | Yes |  |  | It depends on the SDK provided by the scanner device. We can check for an option to capture the quality of document captured during scanning if SDK provides. Need to do some poc on this area.
66 | MOS-13147 | 2018-12-06 | GoM Requirements | Pre-registration | New | OCR as part of Document Upload: 1. As per GoM, MOSIP should support quality check of documents during document upload. Current Implementation: MOSIP will perform basic file validations like file size and file format New requirement as per discussions with Shrikant: MOSIP should support OCR as part of quality check of documents during document upload. | Resham | This should be implemented | <22Jan19> OK |  | 1+ | Approved | Shrikant | 2018-12-18 | 40 | 56 | Yes |  |  | Need more clarity and feedback from UX.
67 |  | 2018-12-12 | Ancillary process flow reviwe with Shrikant/Ramesh: Refer MoM dated: 12-Dec-18 | Registration Client | New | Packet Upload: a. Online Mode: i. Registration completed and Packet created (With/Without EoD Process) ii. Initiate Sync from Client to send RID details to Server iii. Server to acknowledge iv. On successful response of ack. From Server, Client to mark packet as “Ready for upload” and initiate auto-upload of packet b. Offline Mode/Low Bandwidth Connection: i. Registration completed and Packet created (With/Without EoD Process) ii. Initiate Sync from Client to send RID details to Server - If connection available iii. Server to acknowledge iv. On successful response of ack. from Server, Client to mark packet as “Ready for upload” v. Packets to be extracted to an external hard drive vi. Packets to be manually uploaded to server | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-12 | 12 | 18 | Yes |  |  | Statsus Updated to Exported for the exported. FilePath should be a configurable one. Offline only export should work. Serice changes, UI changes. EOD Approval Screen On/Off.
68 |  | 2018-12-12 | Ancillary process flow reviwe with Shrikant/Ramesh: Refer MoM dated: 12-Dec-18 | Registration Client | New | Done as MOS 12874 EoD Process: a. Provide ability to configure if EoD process is required/not (Turn On/Off) | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-12 | 4 | 6 | Yes
69 |  | 2018-12-17 | Sprint 6 Demo Feedback from Ramesh/Shrikant/Krishnan | Registration Client | New | Done as MOS 1204 Pre-registration Data Download: 1. In online mode, on input of PRID, system should trigger an additional validation to check if pre-registration data available is the latest/updated data > Fetch latest data > Override existing downloaded data 2. In offline mode, on input of PRID, system to fetch the existing downloaded pre-registration data > Modifications can be made if required (No change) | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-17 | 10 | 15 | Yes |  |  | 1. Pre-Reg Sync/Batch Job Changes 2. Multi-lingual changes 3. ID object based strucutre changes
70 | MOS-13265 | 2018-12-17 | Sprint 6 Demo Feedback from Ramesh/Shrikant/Krishnan | Pre-registration | New | Trigger Notification: 1. Provide an option to add additional Mobile numbers/e-mail IDs to trigger registration confirmation notification to additional recipients as required Assumptions: - To multiple email IDs and/or Mobile Numbers - Audit but not store or map additional IDs/Numbers to applicant - Do not pre-populate the additional IDs/Numbers during Registration - Process should be configurable | Resham | This should be implemented | <22Jan19> Not really needed by GoM, but has been demoed to them. So do it. |  | 1 | Approved | Shrikant | 2018-12-18 | 6 | 12 | Yes |  |  | RPT- it is assumed that the email id is temporarily entered by user and NOT persisted.
71 | MOS-12989 | 2018-12-17 | Sprint 6 Demo Feedback from Ramesh/Shrikant/Krishnan | Registration Client | New | Trigger Notification: 1. Provide an option to add additional Mobile numbers/e-mail IDs to trigger pre-registration confirmation notification to additional recipients as required Assumptions: - To multiple email IDs and/or Mobile Numbers - Audit but not store or map additional IDs/Numbers to applicant - Do not pre-populate the additional IDs/Numbers during Registration - Process should be configurable | Resham | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2018-12-18 | 6 | 9 | Yes
72 |  | 2018-12-20 | Discussion with Sanjay Jain: 13-Dec-18 | Registration Client | De-scoped | DoB Verified/Not Verified Field: - UI level the field “DoB Verified/Not verified” is not required - PoB/other docs can be marked as mandatory/optional vide config but the Country - Backend validations can be plugged in by SI – MOSIP design to accommodate the same | Resham | This is de-scoped |  |  | NA | Approved | Shrikant | 2018-12-18 | 0 | 0 | NA
73 | MOS-13152 | 2018-12-20 | GoM Gap Analysis document discussion with Shrikant | Registration Processor | New | Validation of Master Data: Validation of data in registration packet with master data | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-18 | 20 | 30 | Yes | Dev yet to start | Sprint 9 | (Clarified By Shravan) We will use a Mapping JSON to identify Packets with Master Data and Validate the Same using Kernel Master Data If New Master Data is added there will be Code Changes for this Validation
74 | MOS-12822 | 2018-12-20 | GoM Gap Analysis document discussion with Shrikant | Registration Processor | New | Timestamp Validation: Timestamps validation refers to the validation of time at two levels: - Verification to check if a Registration machine is active at the time of registration, is covered during packet processing - Verification to check if a Registration was carried out on a holiday - Time taken for individual activity is not controlled by MOSIP as this will lead to exlusion in remote areas, however, this will be logged. | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2018-12-18 | 10 | 15 | Yes | Dev in Progress Kernel is developing API for the same | Sprint 8 | Validation of Packet Created During Working Hours will be taken Up in Sprint 8
75 | MOS-13518 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Biometrics Data Capture Screen: 1. Post maximum retry attempts (3) have been reached, system to identify the best quality captured 2. Further to crossing the 3 attempts > If the quality is not met - MOSIP to provide an option to mark the iris, finger as exception and proceed further – Biometrics in this case should be re-captured - New requirement 3. Provide an option to mark a reason for Biometrics Exception > Missing finger or Missing iris or Low quality - New requirement | Resham | This should be implemented |  | This should be part of v1-GoM. Requirement: Further to crossing the 3 attempts > If the quality is not met - MOSIP to identify the best of the captured biometrics and automatically mandate capture of exceptions photo (This is not an additional photo) Estimates to be re-visited and UI to be updated. | 1+(Earlier V1) | Approved | Shrikant/ Ramesh | 2018-12-31 | 12 | 18 | Yes |  |  | Device + SDK required for actual bio- implementation.
75 | MOS-15999 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Biometrics Data Capture Screen: Stubbed Implementation Implementation 1. Post maximum retry attempts (3) have been reached, system to identify the best quality captured 2. Further to crossing the 3 attempts > If the quality is not met - MOSIP to provide an option to mark the iris as exception and proceed further – Biometrics in this case should be re-captured - New requirement 3. Provide an option to mark a reason for Biometrics Exception > Missing iris or Low quality - New requirement | Resham | This should be implemented |  | NA as functionality to be provided as part of v1 | 1+(Earlier V1) | Approved | Shrikant/ Ramesh | 2018-12-31 | 4 | 6 | Yes |  |  | Device + SDK required for actual bio- implementation.
76 | MOS-13519 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Capture Biometrics Exception Photo: 1. Provide ability to capture multiple photos based on each reason and for example, one photo for fingerprint and one photo for iris exception – Either refer or capture different photo for each exception - New requirement 2. Provide ability to upload documents to support exceptions - New requirement | Resham | This should be implemented |  | Pending till finding a Use Case & demand from a adopter country. Can be moved to 1+ as on date. | 1+(Earlier V1) | Approved | Shrikant/ Ramesh | 2018-12-31 | 30 | 45 | Yes
77 | MOS-13522 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Operator Authentication: 1. Provide ability to capture live photo (Maybe a short video instead of a photo) – New requirement | Resham | This should be implemented |  | > In v1 - Include Operator Iris and Face Authentication - Estimates to be provided. > Liveness detection and video capture can be moved to v2 and implemented based on demand. | 2(Earlier V1) | Approved | Shrikant/ Ramesh | 2018-12-31 | 20 | 30 | Yes |  |  | Cbeff update applicable.
78 | MOS-13523, MOS-13659 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Biometrics Exceptions Approval: 1. In case of biometric exceptions, provide ability to configure if supervisor authentication is required and if it is one/two levels – Two levels of Supervisor approval is a New Requirement | Resham | This should be implemented |  | This can be moved to v1+ | 1+(Earlier V1) | Approved | Shrikant/ Ramesh | 2018-12-31 | 6 | 9 | Yes
79 | MOS-13524 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | UIN Update: i. Provide ability to scan QR code besides manually entering UIN number - New requirement ii. Additionally, pre-populate data from QR code (if available), based on option selected for update (EG: If address is marked for update, then address to be pre-populated from QR code). Implementation aspects to be discussed - New requirement iii. Evaluate if CNIE/UIN/EC Number Update is required, as if the number captured is incorrect, packet processing would have failed – Place in CR tracker if excluded | Resham | This should be implemented |  | This can be moved to v1+ | 1 | Approved | Shrikant/ Ramesh | 2018-12-31 | 30 | 45 | Yes |  |  | QR - hardware - SDK - integration. [Need to identify the open source lib + drivers + hardware]
80 |  | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Registration Processor | De-scoped | Manual Adjudication: i. MOSIP will provide the required demographic and biometric data to be consumed by Biometrics Service Provider ii. User Interface for manual adjudication will be provided by Biometrics Service Provider (BSP) and can be de-scoped to v2 of MOSIP | Resham | This can be implemented based on demand - No requirement identified in v1 |  |  | NA | Approved | Sanjay | 2019-01-12 | 0 | 0 | NA | Dev Not Needed (De-Scoped) | NA | Manual Verification as part of CNIE data mis-match would be part of SI scope, as concluded during the conference call with GoM/PwC on 12Dec’19 – Refer atatched mail (Point 1.d.iv) On the Manual Verification post biometric deduplication failure – This has been de-scoped to v2 of MOSIP (Tracked in the Features Roadmap tracker).
81 | MOS-15998 | 2018-12-31 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | UIN Update: Stub for QR data retrieval i. Provide ability to scan QR code besides manually entering UIN number - New requirement ii. Additionally, pre-populate data from QR code (if available), based on option selected for update (EG: If address is marked for update, then address to be pre-populated from QR code). Implementation aspects to be discussed - New requirement iii. Evaluate if CNIE/UIN/EC Number Update is required, as if the number captured is incorrect, packet processing would have failed – Place in CR tracker if excluded iv.For Registration Client, admin should configure the “Biometrics Exceptions Applicable” as one of the attributes driving the “Applicant Type”, for which a specific set of Document Categories and its respective Document Types can be setup by the admin. – This has been confirmed with the customer | Resham | This should be implemented |  | This can be moved to v1+ | 1 | Approved | Shrikant/ Ramesh | 2018-12-31 | 10 | 15 | Yes |  |  | Stub for QR data retrieval. UI + Api changes.
82 |  | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Registration Client | New | Virus Scan of Registration Client Software: i. To be included, considering usage of Windows OS by GoM (Even though within Govt. Network) | Resham | This should be implemented | If a virus is detected what actions should be available to the user? [Ramesh, 17/1/19] All options are outside of the software. We don’t have to do anything. We should alert the user. | To be provided in v1 | 1 | Approved | Ramesh | 2019-01-12 | 20 | 30 | Yes |  |  | if the Registration client software is a docker then we have to check the feasibility of the same.
83 | MOS-13526 | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Registration Client | New | Virus Scan of each Registration packet in Registration Client Software: (Prior to packet upload) i. To be included, considering usage of Windows OS by GoM (Even though within Govt. Network) | Resham | This should be implemented | If a virus is detected what actions should be available to the user? [Ramesh, 17/1/19] All options are outside of the software. We don’t have to do anything. We should alert the user. | To be provided in v1 | 1 | Approved | Ramesh | 2019-01-12 | 6 | 9 | Yes
84 | MOS-13528 | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Admin/ Reporting | New | Lost UIN: i. MOSIP design accommodates an elevated user within the MOSIP eco-system to view data of a UIN holder ii. This will help facilitate usage of this API by internal users to ease the process of retrieving Lost UIN online, without biometrics iii. It is recommended not to expose the Lost UIN feature on a public portal | Resham | This should be implemented | Should this be on the client or admin portal? How will partial matches be handled? [Ramesh, 17/1/19] This should be an exact match. Let us provide an API and the feature as part of an admin portal. Not needed in the registration client as of now. |  | 1 | Approved | Sanjay | 2019-01-12 | 0 | 0 | NA |  |  | This functionality has been removed. Need confirmation.
85 | MOS-13157 | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | ID Authentication | New | Approach of Authentication by AUA vide TSP (ASA): i. User Agency (AUA) to sign and send request for authentication to TSP (ASA) ii. TSP (ASA) to perform network authentication of source of data (Could be VPN/SSL checks) iii. If ok, ASA to sign the packet > Transmit to MOSIP system iv. MOSIP to perform check on authenticity of TSP signature and honor auth request accordingly | Resham | This should be implemented | <22Jan19> It is really subset of 61, please merge the two. Needs to be implemented for v1. |  | 1 | Approved | Sanjay | 2019-01-12 |  | 50 | Yes | Dev to Start | Sprint 9 | <20/02/2019> One Partner would be mapped to multiple policies. Policies attached to a Partner needs to be validated against Auth requested. Partner and their digital signature verification would also be done before processing Auth/eKYC Requests.
86 | MOS-13161 | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | ID Authentication | New | Additional eKYC API for authentication by an authorized agency: i. GoM will require an additional API ii. MOSIP to provide an additional API to fetch specific data of an individual based on UIN number (Evaluate security aspect, as linking of HoF and maintenance of family relationship will be required as a security imperative) and send to Social Protection Data System iii. MOSIP to provide a mechanism to record the consent of HoF iv. This is required to accommodate Household Program of GoM | Resham | This should be implemented | <22Jan19> It is in scope of v1. Need design (using modularity principles) and effort estimate |  | 1 | Approved | Sanjay | 2019-01-12 |  |  |  |  | Sprint 11 | Awating requirement clarification from GoM for CR estimation
87 |  | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Admin/ Reporting | New | Reporting: i. MOSIP to run a periodical check on Update Packets received to update “Status” – To verify if transactions have been carried out post reporting of UIN for death/de-activation ii. Report to be drawn on the same | Resham | This should be implemented | <22Jan19> We need to do it. Need to see design & Effort estimate |  | 1 | Approved | Sanjay | 2019-01-12
88 |  | 2019-01-12 | Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Technology | New | Use of ISILON Hadoop in RNP System: i. MOSIP to incorporate usage of ISILON/HDFS ii. Implication on testing to be evaluated iii. Biztalk | Resham | This should be implemented |  |  | 1 | Approved | Sanjay | 2019-01-12
89 | MOS-13527 | 2019-01-21 | Mail from Ramesh dtd 21Jan19_Reference Meeting with GoM/PwC/MOSIP Tech Board - 12Jan'19 | Registration Client | New | USB Bootable Dongle vs Downloadable Software: 1. The USB dongle work can be de-prioritized for Morocco. We need to make sure that we can work with the TPM for keys to be stored on Windows 10. Also need to check if docker allows access to TPM on Windows 10. 2. From a deployment guideline perspective we have to advise morocco to enable bitlocker for encryption of hard drive. 3. We can look at USB dongle later as part of Vanilla version of MOSIP | Resham | This should be implemented |  | OK | 1 | Approved | Ramesh | 2019-01-21 | 40 | 60 | Yes |  |  | Need some analysis on this area. Approximate effort provided. Based on R&D this effort would vary. [TPM + Bitlocker + Windows + Docker]
90 |  | 2019-01-24 | Internal requirement evaluation dt. 14 Dec '18 | Registration Client | New | Packet Clean-up: Delete pre-reg packet if not consumed in client after 15 days of appointment date. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2019-01-24 | 4 | 6 | Yes
91 | MOS-13556 | 2019-01-24 | Internal requirement evaluation | Registration Client | New | Enter Pre-registration ID: Addendum to MOS-1204: 1. Provide ability to scan the pre-reg ID using a QR code scanner and populate the ID on the registration page. | Vivek/Akshaya | This should be implemented |  | This can be moved to v1+ | 1+ | Approved | Shrikant | 2019-01-24 | 30 | 45 | Yes |  |  | Need to procure the QR scanner device. Identify the opensource lib to communicate with QR scanner driver. Integrate from Reg. client application.
92 | MOS-13556 | 2019-01-24 | Internal requirement evaluation | Registration Client | New | Enter Pre-registration ID: Addendum to MOS-1204: Stubbed data 1. Provide ability to scan the pre-reg ID using a QR code scanner and populate the ID on the registration page. | Vivek/Akshaya | This should be implemented |  | NA | 1+ | Approved | Shrikant | 2019-01-24 | 6 | 9 | Yes |  |  | Stubbed data.
93 | MOS-13556 | 2019-01-24 | Internal requirement evaluation | Registration Client | New | Enter Pre-registration ID: Addendum to MOS-1204: With Stub data for QR code data 1. Provide ability to scan the pre-reg ID using a QR code scanner and populate the ID on the registration page. | Vivek/Akshaya | This should be implemented |  | NA | 1+ | Approved | Shrikant | 2019-01-24 | 10 | 15 | Yes |  |  | With Stub data for QR code data.
94 | MOS-13557 | 2019-01-08 | MoM dated 08Jan'19 - Refer email SUB: MoM: Applicant Type Mapping - Requirement Clarification <08-Jan'18> | Registration Client | New | Document Upload: Addendum to MOS-1214: 1. Document Categories + Types applicable for an individual are driven by configuration per Applicant Type + Gender + Foreigner/Local+Biometrics Exceptions Applicable (“Biometrics Exceptions Applicable” should be considered as one of the attributes driving the “Applicant Type”, for which a specific set of Document Categories and its respective Document Types can be setup by the admin) 2. Applicable documents are always mandatory. There is no optional document. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2019-01-02 | 12 | 18 | Yes
95 | MOS-13344 | 2019-01-08 | MoM dated 08Jan'19 - Refer email SUB: MoM: Applicant Type Mapping - Requirement Clarification <08-Jan'18> | Pre-registration | New | Document Upload: Addendum to MOS-1214: 1. Document Categories + Types applicable for an individual are driven by configuration per Applicant Type + Gender + Foreigner/Local. 2. Applicable documents are always mandatory. There is no optional document. | Resham | This should be implemented |  |  | 1 | Approved | Shrikant | 2019-01-02
96 |  | 2019-01-24 | Internal evaluation and discussion with Shrikant between 8 Jan and 14 Jan '19 | Registration Client | New | Preview Page: Addendum to MOS-1214: 1. Provide a timer (default 30 sec). User can proceed to the next step only after expiry of the timer. 2. Preview page should display actual scanned images of fingerprints and irises. 3. On navigating to Registration Preview > Edit > Modify ‘Biometric Exception’ from ‘On’ to ‘Off’ or ‘Off’ to ‘On': All biometrics previously captured (including photos) should be cleared and fresh captures will need to be made. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2019-01-14 | 10 | 15 | Yes
97 | MOS-13559 | 2019-01-24 | Internal evaluation and discussion with Shrikant between 8 Jan and 14 Jan '19 | Registration Client | New | Acknowledgement Page: Addendum to MOS-338: Render dummy images of left hand, right hand, thumbs, left iris and right iris. A tick or cross against each finger/Iris should indicate if the respective biometric was captured or was marked as an exception. Show fingerprint quality ranks. Remove fingerprint. For Morocco, it should be disabled/enabled depending on the config | Vivek/Akshaya | This should be implemented |  | To be provided in v1 with FP | 1 | Approved | Shrikant | 2019-01-14 | 6 | 9 | Yes |  |  | Display the bio-metric quality detail based on what captured in previous screens.
98 | MOS-13560 | 2019-01-24 | Internal evaluation and discussion with Shrikant between 2 Jan and 3 Jan '19 | Registration Client | New | UIN Update: Addendum to MOS-1299: 1. The mandatory biometrics should be configurable. For v1 we will implement the following rules. 1.1. UIN Update - Adult - Update of demographic data only: Capture at least one biometric (fingerprint or iris). More than one can be captured at the operator’s discretion. - Update of fingerprints: Capture all ten fingerprints minus any exceptions. - Update of irises: Capture both irises minus any exceptions. 1.2. UIN Update - Child - for the first time after turning 5 - Capture all ten fingerprints and both irises minus any exceptions. - Capture at least one biometric of the parent. 1.3. UIN Update - Child - before 5 years of age - Only demographic data update is allowed. Capture at least one biometric of the parent. 2. Mandatory fields to be captured and sent in the packet: UIN, List of attributes marked for update, New values of attributes, Full Name, Face photo. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Shrikant | 2019-01-03 | 10 | 15 | Yes |  |  | with actual bio device implementation [ FP, IRIS and Face]
99 | MOS-13561 | 2019-01-24 | Sprint 7 Demo Feedback from Ramesh/Shrikant/Krishnan | Registration Client | New | Upload Packets: Addendum to MOS-559: 1. Provide the ability for the Officer to first view packet IDs pending upload and select which ones to upload. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Ramesh | 2019-01-24 | 6 | 9 | Yes
100 | MOS-13562 | 2019-01-24 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Device Status: Display device status on the header. | Vivek/Akshaya | This should be implemented |  | To be provided in v1 | 1 | Approved | Ramesh | 2019-01-24 | 10 | 15 | Yes |  |  | UI Mock required… relying on the device specific SDK… 10 PDs [IRIS, Face, QR, ]
101 | MOS-15996 | 2019-01-24 | Feedback during review of VDs - Refer MoM dated 31-Dec-18 | Registration Client | New | Device Status: Stubbed Implementation Display device status on the header. | Vivek/Akshaya | This should be implemented |  | NA | 1 | Approved | Ramesh | 2019-01-24 | 4 | 6 | Yes |  |  | With stubbed value.
102 | MOS-10831 | 2018-12-14 | Requirements Review of FIT2 stories | ID Authentication | New | Fingerprint and IRIS Auth Composite Score Logic For the Fingerprint and IRIS Composite Authentication, the composite score logic for two fingerprints/IRIS to be provided by SDK MOSIP to integrate with SDK provided by the country to retrieve the composite score | Hema | This should be implemented |  |  | 1 | Approved | Ramesh | 2018-12-14 | 20 | 40 | Yes | Dev to start | Sprint 12
103 | MOS-13664 | 2018-12-13 | Auth API spec changes based on technical Review | ID Authentication | New | Design Changes based on technical Review | Hema | This should be implemented |  |  | 1 | Approved | Sanjay | 2018-12-13 |  | 30 | Yes | Dev to start | Sprint 10 | Awaiting clarifications for CR #85 and #86 <20/02/2019> Changes corresponding to API Specification changes would be incorporated
104 | MOS-13682 | 2019-01-30 | Query log clarification: Refer email dated 30Jan'19 | Pre-registration | New | Individual's Consent on Data Sharing: On initiating a new application, before entering the demographic data, MOSIP should provide an explicit option (Recommend a pop-up with check-box to give consent) to the individual to give his/her consent for storing/utilizing the data as appropriate. This consent should be sought for every applicant. | Resham | This should be implemented as per the change description. |  |  | 1 | Approved | Shrikant | 2019-01-30
105 | MOS-14046 | 2019-01-30 | Query log clarification: Refer email dated 30Jan'19 | Registration Client | New | Individual's Consent on Data Sharing: For every registration, MOSIP should provide an option for the RO to mark an individual's consent. This should be provided on the "Preview" page. The options provided should be: Yes/No. If the RO marks "No" for a specific registration, this should not inhibit issuance of UIN for that individual. Whether the consent is marked as Yes/No should not have any impact on issuance of UIN for that individual and MOSIP should not execute any validations in this regard during packet processing. | Resham | This should be implemented as per the change description. |  | To be provided in v1 as per change description. Consent data should be definable by the Country. If the consent is marked as No, SI will build rules around it. | 1 | Approved | Shrikant | 2019-01-30 | 4 | 6 | Yes |  |  | TBD with Shrikant/Ramesh so as to be align with Pre registration requirement
111 | MOS-13344 MOS-12060 MOS-13950 MOS-13951 MOS-13962 MOS-12068 MOS-13976 | 2018-01-08 | MoM dated 08Jan'19 - Refer email SUB: MoM: Applicant Type Mapping - Requirement Clarification <08-Jan'18> | Kernel | New | Applicant Type-Document Category/Type Mapping: Ability to maintain Applicant Type-Document Category-Document Type Mapping | Amandeep | This should be implemented |  |  | 1 | Approved | Ramesh | 2019-01-08 |  | 30 | Yes |  | Sprint 9
112 | MOS-13138 | 2018-01-08 | MoM dated 08Jan'19 - Refer email SUB: MoM: Applicant Type Mapping - Requirement Clarification <08-Jan'18> | Registration Processor | New | Applicant Type-Document Category/Type Mapping: Applicant Type-Document Category-Document Type Mapping | Rounak | This should be implemented |  |  | 1 | Approved | Ramesh | 2019-01-08 | 10 | 15 | Yes
113 | MOS-13943 | 2018-12-02 | Process Flow Validations Discussion for Reg. processor with Vivek Raghavan | Kernel | New | Master Data Valiadtion during Packet Processing: Due to the additional item for Reg Processor - MOS-13152 - To implement Master Data Validation in ID Object during packet processing, this will be a CR for Kernel: Fetch the Location Data based on the Location Name | Amandeep | This should be implemented |  |  | 1 | Approved | Shrikant | 2019-01-08 | 2 | 3 | Yes |  | FIT-3
114 | MOS-13944 | 2018-12-02 | Process Flow Validations Discussion for Reg. processor with Vivek Raghavan | Kernel | New | Master Data Valiadtion during Packet Processing: Due to the additional item for Reg Processor - MOS-13152 - To implement Master Data Validation in ID Object during packet processing, this will be a CR for Kernel: Fetch Gender Data based on a Gender Name | Amandeep | This should be implemented |  |  | 1 | Approved | Shrikant | 2019-01-08 | 2 | 3 | Yes |  | FIT-3
115 | MOS-13945 | 2019-01-31 | Refer MOM:MoM_MOSIP_Full_Demo_Kernel_Customer_Meeting_31Jan19 | Kernel | New | Sync Approach Change: Ability to respond to Registration Client with "Last Sync Timestamp" while syncing Masterdata, List of Users, Roles and User-Role Mapping to Registration Client | Amandeep | This should be implemented |  |  | 1 | Approved | Ramesh | 2019-01-31 | 2 | 3 | Yes |  | FIT-3
116 | MOS-14005 | 2019-01-31 | Refer MOM:MoM_MOSIP_Full_Demo_Kernel_Customer_Meeting_31Jan19 | Kernel | New | License Key Status: Ability to maintain various status for a License Key Ability to temporarily suspend or permanently block a License Key | Amandeep | This should be implemented |  |  | 1 | Approved | Ramesh | 2019-01-31 | 4 | 8 | Yes |  | FIT-3
117 | MOS-15406 | 2019-01-31 | Refer MOM:MoM_MOSIP_Full_Demo_Kernel_Customer_Meeting_31Jan19 | Kernel | New | UIN Status: Introduce an intermediary status for UIN to indicate the difference between UIN issuance and UIN allocation | Amandeep | This should be implemented |  |  | 1 | Approved | Ramesh | 2019-01-31 |  | 11 | Yes |  | Sprint 9
118 | MOS-15404 | 2019-01-31 | Refer MOM:MoM_MOSIP_Full_Demo_Kernel_Customer_Meeting_31Jan19 | Kernel | New | Token ID Generation: Change the Token ID generation algorithm from Hash to random generation |  |  |  |  | 1 | Approved | Ramesh |  |  | 12 | Yes |  | Sprint 9
119 | MOS-15408 | 2019-02-01 | FW: MOSIP Demo: Kernel <31st Jan,19> Seeking clarity on extended Sync Feature for Reg. Client | Kernel | New | Sync Handler: There will an additional method for registration client to sync master data where they will send Registration Center id and machine id. This will be to validate whether a particular machine is still mapped to the received Registration Center or not |  | This should be implemented as per the description |  |  | 1 | Approved | Ramesh |  |  | 5 | Yes |  | Sprint 9
120 |  | 2019-02-21 | Mail from GoM on the pending inputs | Pre-registration | New | Location Hierarchy Update: 1. Update Location Hierarchy as per the structure received from GoM with the following fields: House Number, Building, Avenue/ street/Road/Path, District / residence/area/ bloc of buildings / Douar, ZIP Code, City, Town, Village a. Fields: City, Town & Village: Values should be hierarchically derived from the Postal Code selected b. Each Postal Code can be mapped to one or multiple Cities c. Each City could be mapped to one or multiple Towns d. Each Town could be mapped to one or multiple Villages e. If only one value is found to be associated to the selected Postal Code, then the mapped City, Town and Village should be automatically rendered f. If more than one value is found to be associated to the Postal Code, then the relevant values for City, Town and Village should be rendered 2. DB structure and UI to be updated accordingly |  | This should be implemented as per the description |  |  | 1 | Approved | Shrikant | 2019-02-21
121 | MOS-16544 | 2019-02-21 | Mail from GoM on the pending inputs | Registration Client | New | Location Hierarchy Update: 1. Update Location Hierarchy as per the structure received from GoM with the following fields: House Number, Building, Avenue/ street/Road/Path, District / residence/area/ bloc of buildings / Douar, ZIP Code, City, Town, Village a. Fields: City, Town & Village: Values should be hierarchically derived from the Postal Code selected b. Each Postal Code can be mapped to one or multiple Cities c. Each City could be mapped to one or multiple Towns d. Each Town could be mapped to one or multiple Villages e. If only one value is found to be associated to the selected Postal Code, then the mapped City, Town and Village should be automatically rendered f. If more than one value is found to be associated to the Postal Code, then the relevant values for City, Town and Village should be rendered 2. DB structure and UI to be updated accordingly |  | This should be implemented as per the description |  |  | 1 | Approved | Shrikant | 2019-02-21
122 | MOS-16545 | 2019-02-21 |  | Registration Client | New | RO’s biometrics exceptions to not be captured during User Onboarding |  | This should be implemented as per the description |  |  | 2 | Approved | Shrikant | 2019-02-21
123 |  | 2019-03-01 | Discussion with Sasi - refer email dated 01-Mar-19 | ID Authentication | New | Updated Auth and eKYC API spec based on discussion with Sasi - There will be one MOSIP Device Service spec, which will be one unified service spec for registration and authentication devices: https://github.com/mosip/mosip/wiki/ID-Authentication-APIs |  |  |  |  | 1 | Approved | Ramesh | 2019-03-01
124 |  | 2019-03-01 | Discussion with Sasi - refer email dated 01-Mar-19 | ID Authentication | New | Auth APIs now will be authenticated by Partners using VID only Auth APIs now will be authenticated by Partners using VID only |  |  |  |  | 1 | Approved | Ramesh | 2019-03-01
125 | MOS-17830 | 2019-03-04 | Discussion with Shrikant, Ramesh and Sasi - 04-Mar-19 | Registration Client | New | Lost UIN: Via Registration Client software, Collection of Persons Demographic & Biometric Data, performing a Dedupe and identify the Duplicate and proceed to issue of letter. • At the back end - as first step use the demographic data as filter and then perform a biometric dedupe with the limited set of records, in case of unsuccessful match ignore the demographic data and perform a complete biometric dedupe to identify the duplicate. |  |  |  |  | 1 | Approved | Shrikant | 2019-03-04
126 |  | 2019-03-04 | Discussion with Shrikant, Ramesh and Sasi - 04-Mar-19 | Registration Processor | New | Lost UIN: Via Registration Client software, Collection of Persons Demographic & Biometric Data, performing a Dedupe and identify the Duplicate and proceed to issue of letter. • At the back end - as first step use the demographic data as filter and then perform a biometric dedupe with the limited set of records, in case of unsuccessful match ignore the demographic data and perform a complete biometric dedupe to identify the duplicate. |  |  |  |  | 1 | Approved | Shrikant | 2019-03-04
127 |  | 2019-03-05 | E-mail from Shrikant dated 05-Mar-19 | Pre-registration | New | Auto-logout based on Configuration Parameter: a. Due to in-activity for x mins (as configured), the user should be auto-logged out. Prior to logout, the user should be alerted b. If no action is taken by user, the user will be logged out and data entered should not be auto-saved |  |  |  |  | 1 | Approved | Shrikant | 2019-03-05
128 | MOS-18100 | 2019-03-07 | Sprint FIT-3 Demo feedback from Ramesh | Registration Client | New | Proof of Consent: a. Ability to capture Proof of Consent |  |  |  |  | 2 | Approved | Ramesh | 2019-03-07

## Values
Module
Pre-registration
Registration Client
Registration Processor
ID Authentication
Kernel
Admin
resident portal, Dashboards, Reports

## Pivot
Row Labels | Count of S.No. | Sum of Effort (PDs)
DevOps | 1 | 0
ID Authentication | 8 | 30
Kernel | 3 | 0
Pre-registration | 3 | 0
Registration Client | 27 | 0
Registration Processor | 15 | 0
resident portal, Dashboards, Reports | 7 | 0
Grand Total | 64 | 30

## Status Legends
Color | Description
Clarification on the Requierment is Not Clear
Requierment Clarified - Dev In Progress/Completed
Requierment Clarified - Dev Yet to Start
Requierment is De-Scoped