## Admin Scope
Admin Requirements
Feature | Sub-Feature | Mode | Mode - Details | Dev - Prioritization | Story Title | Acceptance Criteria | Version | Estimates for V1 Features | Priority | Dependency | Comments | Customer Comments
General Features of Admin portal | NA | Front-end |  | Create placeholder in JIRA - Detail later |  |  | v1 |  | Vital |  |  | 1. Language Support: > Labels and messages should come from resource files which support I18N > Implementation in English (Labels etc) > Data will be displayed in the language as setup - Virtual keyboards should be available for entry of data in specific language 2. Responsive UI: > The UI should be responsive
MOSIP Platform Setup | MOSIP Platform Setup | Back-end | Initial bulk setup of Platform Data through CSV upload Utility | Developed - Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to set up platform data | Setup of MOSIP application data like List of Templates Types, List of Rejection Reasons, etc through a CSV | v1 | 20 | Vital
ID Definition Setup | NA | Back-end | Initial bulk setup of Platform Data through CSV upload Utility | Developed - Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to set up ID Definition | Setup activity that enables the Country admin to mark attributes that formulate the id for a Country - EG: Demographic data fields, Biometric data capture attributes | v1 | 6 | Vital
ID Definition Validator | NA | Back-end | Schema Validator to validate the ID schema | Create placeholder in JIRA - Detail later | As the MOSIP system, I should be able to validate ID Definition |  | v1 |  | Vital
Configuration Setup | Initial Setup | Back-end | Initial Setup/Update through Config Server | Developed - Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to set up configurations |  | v1 | 30 | Vital
|  | UI |  | Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to set up configurations |  | v2 |  | Desirable |  |  | > Available through GIT UI - No additional requirement
| Cofiguration Validator | - | Validation of Configuration File using Config Validator v1.5 Warning on change of Configuration to Admin | Create placeholder in JIRA - Detail later | As the MOSIP system, I should be able to validate configurations |  | v1 |  | Essential
| Update | UI |  | Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to Update configurations |  | v2 |  | Desirable |  |  | > Available through GIT UI - No additional requirement
| View Configurations | UI | Configuration Fetcher : To view configuration on UI Screen | Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to view Configurations ID Definition |  | v1.5 |  | Desirable |  |  | > Available through GIT UI - No additional requirement
Process Flow Setup | Initial Setup | Back-end | Initial Setup/Update through Server | Create placeholder in JIRA - Detail later | As the MOSIP Admin, I should be able to set up Process Workflow | Setup activity that enables the Country to mark/turn a process on/off, as relevant through backend | v1 | 20 | Vital |  | Process Flow Configuration UI out of scope | > Available through GIT UI - No additional requirement
| Initial Setup | UI | Using UI |  | As the MOSIP Admin, I should be able to set up Process Workflow | Setup activity that enables the Country to mark/turn a process on/off, as relevant through UI | v1.5
| Process Flow Configuration Validator | - | Config validator - Ability to validate process flow configurations For v1: Doc Upload config will be checked as below: 1. Doc Upload turned off in Reg. Client but turned on in Reg. Processor will be identified as a conflict For v1.5: 1. Config Validator for Processes 2. Warning on change of Configuration to Admin | Create placeholder in JIRA - Detail later | As the MOSIP system, I should be able to validate Process Workflow Configurations |  | v1 |  | Essential |  |  | > For Doc Upload Process - in v1, For Rest of the validation, in v1.5
| Update | Back-end | Initial Setup/Update through Server | Create placeholder in JIRA - Detail later | As the MOSIP system, I should be able to update Process Workflow Configurations |  | v1.5 |  | Essential |  |  | > Available through GIT UI - No additional requirement
| View | UI |  |  | As the MOSIP system, I should be able to view Process Workflow Configurations |  | v1.5 |  | Desirable
Master Data Setup | Creation - Initial Setup | Back-end | Intitial Setup of Master data through Utility | P1 | As the MOSIP Admin, I should be able to set up Master data | This includes setup of master data like setting up Location Master, Holiday Master, Templates, Zones etc | v1 | 30 | Vital |  |  | > Data import scripts will support import of Master data
| Creation - Subsequent additions | UI |  | P1 | As the MOSIP Admin, I should be able to subsequently add Master data as required |  | v1 |  | Vital |  |  | > Data import scripts will support incremental import of data (For Master Data that would be frequently added) > They will not clean up the database and reinsert data
| View | UI |  | P1 | As the MOSIP Admin, I should be able to view Master data |  | v1 |  | Vital |  |  | > View screen will be a simple label - value display of data in single or multi-column mode based on visual aesthetics and space available. One standard screen should be reusable for all views
| List to make Updates - Activate/Deactivate/Delete | UI |  | P1 | As the MOSIP Admin, I should be able to activate/de-activate Master data |  | v1 |  | Vital |  |  | > List screen will have a paginated list with check-boxes for selection, select all / deselect all / invert selection, sort, search(filter) with the actions to delete, activate / deactivate selection. One standard screen should be reusable for all lists > Only Status of data to be covered - Activate/De-activate/Delete
| Updates - Incremental data updates | Back-end |  | P1 | As the MOSIP Admin, I should be able to update frequently used Master data as required |  | v1 |  | Essential |  |  | > Data import scripts will support incremental import of data to be updated: For Master Data that would be frequently updated > They will not clean up the database but instead update data
|  | UI |  | P1 | As the MOSIP Admin, I should be able to update in-frequently used Master data as required |  | v1.5 |  | Desirable |  |  | > Data import scripts will support incremental import of data to be updated: For Master Data that would be in-frequently updated > They will not clean up the database but instead update data
Navigation | Login Page | UI | Admin Portal with UI | P1 | As the MOSIP Admin, I should be able to log-in the Admin portal | 1. To enable user to Login In through Username and Password. 2. Along with Password, Multifactor Authentiation will be applicable as configured by the country 3. Putting wrong password/biometric for more than 3 times will lock the account 4. Will also contain link to Forgot Password page (Explained in Password management section) and unblocking an account - Link part of Account Management 5. A user entering wrong password for 3 times (configurable) will get locked and can only be unlocked by a superior admin if Bio Auth not available/by the user if Bio auth is avialable. "Refer Account Management" Feature | v1 | 15 | Vital | Kernel - Authentication | Can country have a policy for Log-in with only Bio and no password If the country only configures Biometric for logging in? What should be the policy for locking the account? How should the unlock happen since only Bio Log-in will eliminate Reset/password Policy
| Logout Page | UI | Admin Portal with UI | P1 | As the MOSIP Admin, I should be able to log-out of the Admin portal | 1. To enable user to Logout 2. User will be Auto logged out after certain time of inactivity. (Period of inactivity: Configurable) | v1 |  | Vital
| Home Page (Profile Management) | UI | Admin Portal with UI | P1 | As the MOSIP Admin, I should be able to navigate on the Admin portal through Home Page | 1. To enable user to land on Home page and navigate through portal 2. Will comprise of options to navigate to User permitted functionalities 3 Will comprise of options for Profile Management (Update his personal details, Account management) | v1 |  | Vital
User Management | User Registration | UI | Admin Portal with UI | P2 | As the MOSIP Admin, I should be able to Register a user on Admin Portal | 1. Admin to register a User by giving required details: Refer "Attributes" sheet 2. Admin will enter the Username as per the pattern decided by the country 3. Map user to a Administrative Geographical Hierarchy - Not needed 4. Send activation link to the user along with User Name on Phone Number and Email 5. Seting up password by user a) User clicks on activation link > User enters VID/UIN for validation b) User enters mobile number > Receives OTP on registered number > User enters OTP and Submits c) System validates UIN d) System performs Demo Auth e) System checks if User is Child or Adult f) If auth successful, system enables field to enter password g) User enters password > User re-enters password h) System generates Token ID using Admin's Partner ID and map it to the User - NA h) System Maps RID to the User in IAM : This will be current/latest RID the user has i) User receives a Notification with Username and link to the portal on Phone number and Email 6. User can start using this account by going to Reg. Client/Admin portal as applicable and logging in by giving username and password (Multi-factor login supported) If activation link expires (expiry time configurable), resend the link through a batch process | v1 | 25 | Vital |  | 1. For addition of MISP, do we need approver? 2. Do we create roles for each functionality? Or do we go with the structure currently decided? "Refer proposed user hierarchy"
| User Registration Approval | UI | Admin UI: No Full flegded workflow implementation will be provided in this version Only maker checker validations ares available for record creation not for updation Bulk activation on UI, no API for bult activation/Deactivation Maintain reason for blocking the account | P2 | As the MOSIP Admin, I should be able to Approve a creation of User on Admin Portal | 1.An Admin (Approver) will approve the Users created by the Admin 2. The Admin creating the Users cannot be same as the Approver 3. If the admin does not approve for a certain period of time a) Reminder Notifications (How many?) b) Change the approver (what happens if we have only one zonal approver for that zone) c) Auto-Approve d) Reject e) Escalation Mail f) Reports | v1 |  | Vital |  | Can this approval workflow change? Like 1 or multi-step approval process? Workflow engine? If we go with the Zonal Admin Approach? Zonal Approvals? No approval in Updates for v1 For V2: Approval process for updates
| View | UI | Admin UI | P2 | As the MOSIP Admin, I should be able to View list of registered Users on Admin Portal |  | v1 |  | Vital
| Update: User Unblocking/Blacklisting/ Whitelisting/De-Activating/Activating | UI | Admin UI | P2 | As the MOSIP Admin, I should be able to Activate/De-Activate/Blacklist/Whitelist a User | 1. A superior Admin can Blacklist/Whitelist a User 2. A superior Admin can De-Activate/Activate a User 3. If a user blocks his/her account, a superior Admin can unblock a users account if contacted by the User. "Refer Login Page Section" 4. If a user wants to reset his/her password and Bio auth is not possible, a superior admin will be able to reset password - A reset password link will be sent to the user on phone number and email 5. if a user wants to retrieve his/her username and Bio Auth is not possible, a superior admin will be able to send username to the user - User will receive a link with his/her username | v1 |  | Vital |  | Blacklisting/Whitelisting/De-Activating/Activating will require Approval No bulk operation through UI, only one-by-one If we deactivate a user, we will deactivate all the related mappings? While activating, manual activation of mappings has to be done
Account Management | Change Password | UI | Admin with UI Only when User is online | P2 | As the MOSIP Admin, I should be able to change password | Change password (Would support Multi Factor Auth - Configurable by the country) a) User to select Change Password option from Reg. Client/Admin portal b) Navigates to the PW Management page > User to provide Old and New PW > Authenticate with OTP (User has to be online) | v1 | 20 | Vital |  | Can country have a policy for Log-in with only Bio and no password If the country only configures Biometric for logging in? What should be the policy for locking the account? How should the unlock happen since only Bio Log-in will eliminate Reset/password Policy | The password management feature is an admin feature. The reg client will only have a button / menu / link that will take the user online to the admin screen / url. The url itself could be a config sent from the server as part of data sync. The menu in the client is a convenience feature, and means that the user has a ready url to go to. Admin module to ensure the Reg. Client requirements are met
| Reset Password | UI | Admin with UI Only when User is online | P2 | As the MOSIP Admin, I should be able to reset password | Reset password (Would support Multi Factor Auth - Configurable by the country) (Only OTP auth if requested through Admin) a) User clicks on Forgot passsword link on Reg. Client Login page/Admin portal Login page b) User inputs user name c) User enters new password d) User confirms new password by entering again e) User generates OTP on registered mobile number f) User puts OTP and submits g) Message displays, "Password Upated". h) User can go to portal to login with new password | v1 |  | Vital |  | For Reset Password? If Bio Auth is configured and BIO capture device is not available? What should be the further process?
| Forgot Password | UI | Admin with UI Only when User is online | P2 | As the MOSIP Admin, I should be able to retrieve username | Forgot Username (Would support Multi Factor Auth - Configurable by the country) (Only OTP auth if requested through Admin) a) User clicks on Forgot Username link on Reg. Client Login page/Admin portal Login page b) User enters his mobile number c) System checks if mobile number is registered or not d) User does OTP Auth e) System sends SMS notification with User Name | v1 |  | Vital
| Account Unblocking | UI | Admin with UI Only when User is online | P2 | As the MOSIP Admin, I should be able to unblock account of users | Account unblocking (Would support Multi Factor Auth - Configurable by the country) (Only OTP auth if requested through Admin) a) User navigates to Login page b) User clicks on "Unblock account page" c) User enters his mobile number d) System checks if mobile number is registered or not e) User does OTP Auth f) System sends SMS notification with User Name | v1 |  | Vital |  |  | - Maintain a configurable time duration between each un-lock attempt (For auto-unlock) - SPVR/Assigned user can intervene to un-lock account immediately
Asset Management | Registration Centers- Initial Creation/Setup | Back-end | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Registration Center Details | 1. Creation of Center on Admin portal based on zones a) Zonal admin will select a Center Type the new Center belongs to. (Center type can be "Regular", "Handicapped Firendly", "Child Frieldly" etc) a) Zonal admin will input required details for the new Center. (Refer Attributes Sheet) b) Center will get mapped to Admin's Zone 2. Update Center related details a) Zonal admin will be able to update Center related details in DB 3. Update Zone of a Center (If a Center is being moved to a new zone or accidently assigned to a wrong zone) a) Zonal admin will have to un-map Users, Machines and Devices mapped to that Center B) Zonal admin will assign the Center to the new zone c) The Center won't be visible to the Zonal admin of the previously assigned zone d) In case of accidently assigning the wrong zone, Zonal Admin will have to get in touch with the Zonal admin of newly assinged zone to get the Center re-assigned to the old zone 4. De-Activating/Re-Activating/De-commissioning a Center a) Zonal Admin can De-Activate/Re-Activate a Center - Status will be "Inactive" b) Zonal Admin can De-Activate/Re-Activate Center from his/her zone only - Status will be "Active" c) Zonal Admin can De-Commision a Registration Center of his Zone which is in his zone. c) Zonal Admin can De-Commision a Registration Center of his Zone which is in his zone. All the respective mappings will be de-activated 5. History will be maintained in the DB for all the updates in the Center Details | v1 | 50 | Vital | Kernel - Fetch Device Type, Fetch Device Spec, Create Device, Update Device, Device ID Generator | 1. Zones created by Country should be at a common geographical level, else the zones will overlap. Will country manage this overlapping of zones or do we restrict overlapping of zones? 2. For Devices and Machine, Do we need zones since mapping them to a center will indirectly map them to a center? If no, any admin can view all devices/machines since there will be no zonal filters available and no way to restrict access
|  |  | Utility and UI to import through CSV/XLS | P1 | As the MOSIP Admin, I should be able to register a Registration Center |  | v1 |  | Vital
| Registration Centers - Subsequent Additions | UI |  | P1 | As the MOSIP Admin, I should be able to add Registration Center(s) | - Incl. UI to import through CSV/XLS | v1 |  | Essential
| Registration Centers - View | UI |  | P1 | As the MOSIP Admin, I should be able to View the list of Registration Center(s) |  | v1 |  | Essential
| Machines - Initial Creation/Setup | Back-end | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Machine Details | 1. Creation of Machine on Admin portal based on zones a) Zonal admin will select a Machine Type and Machine Specification for the new Machine b) Zonal admin will input required details for the new Machine. (Refer Attributes sheet) c) Device will get mapped to Admin's Zone d) Admin will map the Machine to a Center existing in the Admin's Zone e) Mevice uniqeness will be maintained through Serial Number 2. Update Machine related details a) Zonal admin will be able to update Machine related details in DB (E.g Serial Number, Mac-Address) 3. Update Zone of a Machine (If a Machine is being moved to a new zone or accidently assigned to a wrong zone) a) Zonal admin will remove the mapping of the Center and Machine (if already mapped to a Center of another zone) b) Zonal admin will assign the Machine to the new zone c) The device won't be visible to the Zonal admin of the previously assigned zone d) In case of accidently assigning the wrong zone, Zonal Admin will have to get in touch with the Zonal admin of newly assinged zone to get the Machine re-assigned to the old zone e) The Machine needs to be remapped to a new Center once the new zone has been assigned 4. De-Activating/Re-Activating/De-commissioning a Machine a) Zonal Admin can De-Activate/Re-Activate a Machine - Status will be "Inactive" b) Zonal Admin can De-Activate/Re-Activate Machines from his/her zone only - Status will be "Active" c) Zonal Admin can De-Commision a Machine of his Zone which is in his zone. All the respective mappings will be de-activated 5. History will be maintained in the DB for all the updates in the Machine Details | v1 |  | Vital | Kernel - Fetch Machine Type, Fetch Machine Spec, Create Machine, Update Machine, Machine ID Generator
|  |  | Utility to import through CSV/XLS |  | As the MOSIP Admin, I should be able to register a Machine |  | v1 |  | Vital
| Machines - Subsequent Additions | UI |  | P1 | As the MOSIP Admin, I should be able to add Machine(s) | - Incl. UI to import through CSV/XLS | v1 |  | Essential
| Machines - View | UI |  | P1 | As the MOSIP Admin, I should be able to View the list of Machine(s) |  | v1 |  | Essential
| Devices - Initial Creation/Setup | Back-end | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Device Details | 1. Creation of Devices on Admin portal based on zones a) Zonal admin will select a Device Type and Device Specification the new Device belongs to b) Zonal admin will input required details for the new Device (Refer Attributes Sheet) c) Device will get mapped to Admin's Zone d) Admin will map the Device to a Center existing in the Admin's Zone e) Device uniqeness will be maintained through Serial Number 2. Update Device related details a) Zonal admin will be able to update Device related details in DB (E.g Serial Number, Mac-Address) 3. Update Zone of a Device (If a Device is being moved to a new zone or accidently assigned to a wrong zone) a) Zonal admin will remove the mapping of the Center and Device (if already mapped to a Center of another zone) b) Zonal admin will assign the Device to the new zone c) The Device won't be visible to the Zonal admin of the previously assigned zone d) In case of accidently assigning the wrong zone, Zonal Admin will have to get in touch with the Zonal admin of newly assinged zone to get the device re-assigned to the old zone e) The Device needs to be remapped to a new Center once the new zone has been assigned 4. De-Activating/Re-Activating/De-commissioning a Device a) Zonal Admin can De-Activate/Re-Activate a Device - Status will be "Inactive" b) Zonal Admin can De-Activate/Re-Activate Devices from his/her zone only - Status will be "Active" c) Zonal Admin can De-Commision a Device of his Zone which is in his/her zone. All the respective mappings will be de-activated 5. History will be maintained in the DB for all the updates in the Device Details | v1 |  | Vital | Kernel - Fetch Center Type, Fetch Machine Spec, Create Center, Update Center, Center ID Generator
|  |  | Utility to import through CSV/XLS | P1 | As the MOSIP Admin, I should be able to register a Device
| Devices - Subsequent Additions | UI |  | P1 | As the MOSIP Admin, I should be able to add Device(s) | - Incl. UI to import through CSV/XLS | v1 |  | Essential
| Devices - View | UI |  | P1 | As the MOSIP Admin, I should be able to View the list of Device(s) |  | v1
| View & Map: Center to Machine | UI | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Center-Machine mapping | 1. Mapping of a Machine to a Center based on zones a) A Machine can only be mapped to one Center b) One Center can have many machines mapped to it c) Mapping will be permitted only within the same zone as the machine 3. De-activating a mapping of a Machine and a Center - Status will be "Inactive" 4..Re-Activating a mapping of a Machine and a Center - Status will be "Active" a) if there is already an active mapping existing for a Machine and Center, Admin will be prompted of such a situation and mapping won't be allowed 5. History will be maintained in the DB for all the updates in the mappings | v1 |  | Vital | Kernel - Fetch/Create/Update Center-Machine Mapping
|  |  | Utility to import through CSV/XLS | P1 | As the MOSIP Admin, I should be able to map a Machine to a Center
| View & Map: Center to Device | UI | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Center-Device mapping | 1. Mapping of a Device to a Center based on zones a) A Device can only be mapped to one Center b) One Center can have many devices mapped to it c) Mapping will be permitted only within the same zone as the device (As the admin is authorized to) 2. Un-mapping a Device from a Center 3. De-activating a mapping of a Device and a Center - Status will be "Inactive" 4..Re-Activating a mapping of a Device and a Center - Status will be "Active" a) if there is already an active mapping existing for a Device and Center, Admin will be prompted of such a situation and mapping won't be allowed 5. History will be maintained in the DB for all the updates in the mappings | v1 |  | Vital | Kernel - Fetch/Create/Update Center-Device Mapping
|  |  | Utility to import through CSV/XLS | P1 | As the MOSIP Admin, I should be able to map a Device to a Center
| View & Map: Center to User | UI | Setup and Update through Admin Portal with UI | P1 | As the MOSIP system, I should be able to store Center-User mapping | 1. Mapping of a User to a Center based on zones a) A User can only be mapped to one Center b) One Center can have many users mapped to it c) Mapping will be permitted only within the same zone as the user (As the admin is authorized to) 2. Un-mapping a User from a Center 3. De-activating a mapping of a User and a Center - Status will be "Inactive" 4..Re-Activating a mapping of a User and a Center - Status will be "Active" a) if there is already an active mapping existing for a User and Center, Admin will be prompted of such a situation and mapping won't be allowed 5. History will be maintained in the DB for all the updates in the mappings | v1 |  | Vital | Kernel - Fetch/Create/Update Center-User Mapping | 1. Should user receive a notification from MOSIP if his/her zone or center is changed? - Subscription needed for notifications Audit events will be created and notificaiton can be sent based on Subscription
|  |  | Utility to import through CSV/XLS | P1 | As the MOSIP Admin, I should be able to map a User to a Center
| Update Mapping: Center to Machine | UI |  | P1 | As the MOSIP Admin, I should be able to Update the Center to Machine mapping |  | v1 |  | Vital
| Update Mapping: Center to Device | UI |  | P1 | As the MOSIP Admin, I should be able to Update the Center to Device mapping |  | v1 |  | Vital
| Update Mapping: Center to User | UI |  | P1 | As the MOSIP Admin, I should be able to Update the Center to User mapping |  | v1 |  | Vital
| Asset Management Approval | UI | Admin Portal with UI | P1 | As the MOSIP Admin, I should be able to approve creation of assets | We will have approvers for each level of Admins: (Zone based?) 1. Central Approver will approve tasks done by Central Admins such as additions of Zonal Admins and Zonal Approvers 2. Zonal Approver will approve tasks done by Zonal Admins such as additions of Users like Center Head, Supervisor and Officer. 3. Zonal Approver will also approve addition of any Center, Device, Machine, mapping of Center-Device, Center-Machine and Center-User (Actions carried out by Zonal Admins) 4. Zonal Approver can only approve changes done in his/her zone | v1 |  | Essential |  | Can this approval workflow change? Like 1 or multi-step approval process? Workflow engine? If we go with the Zonal Admin Approach? Zonal Approvals?
Security Policy Configuration | NA | Back-end | Admin Portal with UI | P2 | As the MOSIP Admin, I should be able to set up security policies for MOSIP Admins | To be able to configure securiy policies for each application. This would include 1. Session Time out policies 2. Password policies 3. Multi-factor auth policies (wherever applicable) Admin Portal will only be accesed thorugh Whitelisted IP Address Authenticate Users accessing the portal At Role Level : Configure Level of AuthN Default Policy: 1. What type of Auth 2. Which would be compulsory in case of multi factor auth 3. Minimum number of factors of Auth (Non-Bio/Bio) 4. Feature Specific auth overwrides Role Specific Behaviour for Reset Password/Forgot Username) | v1 | 15 | Vital
UIN Activation/De-activation | NA | UI | Admin Portal with UI | P2 | As the MOSIP Admin, I should be able to De-activate/Activate a UIN | To enable an Admin to De-Activate or Re-Activate a UIN : Change status This feature will also de-activate or re-activate coresponding VIDs | v1 | 5 | Vital |  |  | Maintain status - Suspended/Suspension revoked
MISP Management | Creation of MISP | UI |  | P2 |  |  | v1.5 |  | Desirable |  |  | Back-end APIs will be done as part of Partner Management Portal
| Mapping a new License Key to MISP | UI |  | P2 |  |  | v1.5 |  | Desirable

## Attributes
Users
First Name
Last name
Contact Number
Email ID
DOB
VID
Registration Center
Registration Center Name
Longitude
Latitude
Registration Center Type
Address
Working Hours
Contact Number
No. of kiosk
Per kiosk Processing time
Starting time
End time
Holiday Zone
Location Code (From location hierarchy)
Location Zone (Zone a Center will belong to based on Zonal Admins zone, currently not in DB)
Machine
Machine Name
Mac Address
IP Address
Serial Number
Machine Spec ID
Location Zone (Zone a Machine will belong to based on Zonal Admins zone, currently not in DB)
Device
Device Name
Mac Address
IP Address
Serial Number
Device Spec ID
Location Zone (Zone a Device will belong to based on Zonal Admins zone, currently not in DB)

## Proposed User Hierarchy
Sample User Hierarchy
1. Central Admin: Manage Zonal Admins, Zonal Approvers, MISP Admins
2. Central Approvers: Approves Created Users
3. Zonal Admin: Manage users like Operators/SPVRs/Center Heads, Device Management, Machine Management, Center Management
4. Zonal Approvers: Approves Users, Centers, Machines and Devices created by Zonal Admins
5. Reg. Centre Head: Unblock account for SPVR and Operator
6. SPVR: EoD Verification
7. Operator: Registration (New/Update/Lost)
Note: Maker and Checker Cannot be same person Update should have approval process System should be flexible enough to map permissions to roles as per the preference of the country - TBD with JOHN
Role code to role name mapping
MISP Creation/Administration will be on Admin Portal

## Password Policy
Password Policy
1. Use of both upper-case and lower-case letters atleast once 2. Use of atleast one numerical digit 3. Use of alteast one of the special characters, such as @, #, $ 4. Restriction on passwords with words found in the User Name and Emaid ID 5. Should not match last three old passwords 6. Minimum character length should be 8

## Values
Vital
Essential
Desirable