## GoM Pre-reg UI
Pre-registration UI: Feedback from GoM_01May'19
S.No | Section/Page | Feedback | Attachment Ref. | Category | Mindtree Comments - 13May19
1 | General | - The GUI of The application is to be reviewed - When refreshing (F5) The page, The user is redirected to The authentication form even if The session is still valid |  | Need Clarity from GoM | Currently system auto-logs out the user on click of refresh. This is the recommended behavior from Security standpoint, part of the design and since data is not saved. However, SI can customize as required.
2 | General | - The mandatory nature of The fields is not mentioned: The user doesn’t know which field is mandatory and which one is not. |  | New Feature/Change | This is WIP with UX team and will be addressed
3 | General | - When choosing The Arabic entry, The direction of The form must be from right to left |  | Clarification Provided | Working as expected in Demographic page.
4 | General | - We need to access to The pre-registration back office to set up all parameters (define field template like phone number, cnie number, consent terms…) |  | Clarification Provided | This is driven by the id definition object and will be provided as part of the Admin module. As part of the 30Jun'19 release, this will be through the backend, wherein admin can setup these aspects. However, UI will not be dynamic based on the fields setup. Any changes required will need to be customized by SI.
5 | Access/Login screen to the pre-registration session | - The access to the session is not possible with Phone Number by using OTP: the input mask doesn't take in charge all number phone formats--> it is mandatory to fill 10 digits that begins with the number 9. The country code of Morocco is 00212......... (00212+9 digits) The only possibility to access to the session is by using e-mail | Refer Attachments, S.No. 5 | Clarification Provided | The aspect of number starting with "x" is configurable. The aspect of 10 digits limitation is also configurable (Global Config property) and can be setup by the admin. Guidance can be provided as required. This configurability applies across the Pre-registration application (Login, Demo data page, Notification trigger on Ack. page) MOSIP has implemented with 10 digits limitation and 91 to facilitate feature testing.
6 | Demographic data screen - Consent screen | - The terms and conditions should be displayed and fully scrolled when accessing to the pre-registration form: we need to access to the pre-registration back office to edit the terms and conditions | Refer Attachments, S.No. 6 | Known Issue/Bug | Internal: Currently this is hard coded. However, this is a known gap and will be fixed (MOS-23916) GoM: In 30Jun'19 release, the admin can setup the required template/text through the backend. To be revised before sending to GoM as "already working as expected"
7 | Demographic data screen | - The field “name” should be splitted into two fields: first name and Last name |  | Clarification Provided | This is driven by the id definition object and will be provided as part of the Admin module. In 30Jun'19 release, this will be through the backend, wherein admin can setup these aspects. However, UI will not be dynamic based on the fields setup. Any changes required will need to be customized by SI.
8 | Demographic data screen | - The transliteration of the full name gives a negative result: it is preferable to deactivate the transliteration mode, and for fields such as name last name to give the possibility to the applicant to fill his data in both languages |  | Clarification Provided | As per current implementation, user can enter the text in Primary language, as well as update the transliterated text in Secondary language as required. SI/Country can further configure as described by GoM.
9 | Demographic data screen | - The age field must be in a read mode |  | Clarification Provided | Current Implementation: User can enter DoB or Age. On entering either of the fields, the other is auto-calculated. Need more clarity in comparison with point 11
10 | Demographic data screen | - The date of birth size must not exceed 10 digits (2 for the day field, 2 for the month field and 4 for the year field) or the field must be in a calendar form |  | Clarification Provided | Calendar form was not recommended by our User Experience team, as the user will need to scroll through the calendar to enter age. Validation of number of digits entered is working as expected.
11 | Demographic data screen | - Provide the case of people who do not have the day / month of birth |  | Clarification Provided | Current Implementation: This scenario has been accommodated. If the user provides age, the system will consider current year > auto-calculate the Year of birth > And assign a default date/month of birth - The default date/month of birth is configurable. Need more clarity in comparison with point 9
12 | Demographic data screen | - The format of cnie field isn’t the same neither for the foreigner ID nor for the EC ID. We need to differentiate between the three fields RNP team can share the format of the three kinds of field later on |  | New Feature/Change | Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
13 | Demographic data screen | - Phone number: The input mask is not working for Moroccan numbers--> in the current version it is obligatory to type a number that begins with 9 followed by 9 digits if not there is a message error of invalid number. the Moroccan phone number is composed of 00212+9digits | Refer Attachments, S.No. 13 | Clarification Provided | The aspect of number starting with "x" is configurable. The aspect of 10 digits limitation is also configurable (Global Config property) and can be setup by the admin. Guidance can be provided as required. This configurability applies across the Pre-registration application (Login, Demo data page, Notification trigger on Ack. page) MOSIP has implemented with 10 digits limitation and 91 to facilitate feature testing.
14 | Demographic data screen | - In the current tested version, the input mask of CNIE and EC is a number of a minimum of 10 digits, in general, ID number is alphanumerical (format of cnie number: AX000000: 2 alphabetic digits+6 numerical digits). RNP team can share the format of the three kinds of field |  | New Feature/Change | Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
15 | Demographic data screen | - Cnie/Ec field should be manadatory, currently, try not to fill this field and you will pass through without error message |  | Clarification Provided | This field is currently mandatory and the validation is implemented.
16 | Demographic data screen | - For applicants under the age of 5, data about the parents or guardian (name and the NIU) doesn't exist. This information is mandatory ( ie: aadhaar) |  | Clarification Provided | Since this is pre-registration, wherein the primary motive is to capture basic data and book an appointment, this ancillary data of the Parent is not imposed on the user/captured at this point. However, this will be mandated during Registration process. Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
17 | Demographic data screen | - For foreigners, there is no field that indicates where to fill the Residency Number--> we suggest to add to the label of CNIE/EC field the residency card number or to adjust the label of that field as per the type of residency selected (citizen or resident) |  | New Feature/Change | Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
18 | Demographic data screen | The latest address structure agreed upon is not implemented in the current version: - The districts and the avenues are not integrated in the form. Those items must replace the fields adresse, adresse ligne 2 and adresse ligne 3 - The zip code is not a combobox, it’s a free inupttext component - There’s no type of house in the address as described (number of house / building and apartment number) |  | Clarification Provided | The new address location hierarchy is yet to be implemented. Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
19 | Demographic data screen | - The fields (Région, Province, ville, Autorité Administrative locale and postal code) must be positioned in the form before the rest of address fields |  | New Feature/Change | Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
20 | Demographic data screen | - The rule of Unicity regarding phone number and E-mail is not integrated in the current version. This rule should apply for adults |  | Clarification Provided | Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
21 | Upload documents screen | - The number of required documents can exceed two: for example in the case the declarant is "a guardian" the proof of relationship with the concerned applicant should be uploaded also |  | Clarification Provided | The Admin can setup the required document category and the document type for each Applicant Type (Adult/Child/Foreginer etc..). Currently PoI, PoA and PoR can be uploaded. Further, Country can customize as required based on 30Jun'19 code release. The provided UI is generic and Country agnostic.
22 | Upload documents screen | - The feature of selecting the document "same as" another applicant is not working: in case of selecting the document "same as" another applicant, this document can’t be displayed | Refer Attachments, S.No. 22 | Known Issue/Bug | This is a known issue - MOS-23912
23 | Applicant data display (Preview) screen and pre-registration receipt (Acknowledgement) screen | - The zip code is not displayed in the summary interface - The three free address fields are not displayed |  | Clarification Provided | The Preview page renders the complete address. The Acknowledgement page comprises of the basic details of User and detailed infor on the appointment date/venue, from a privacy perspective. However, SI/Country may customize as required.
24 | Applicant data display (Preview) screen and pre-registration receipt (Acknowledgement) screen | - The Arabic text in the form should be from right to left | Refer Attachments, S.No. 24 | Clarification Provided | This is a known issue - MOS-21367
25 | Pre-registration receipt (Acknowledgement) screen | The receipt format is to be reviewed - When we read the QR code, we find a number different from the pre-registration ID. |  | Known Issue/Bug | This is a known issue - MOS-15054
26 | Pre-registration receipt (Acknowledgement) screen | The receipt format is to be reviewed - When the user want to send the receipt by e-mail and / or phone, the application shows a popup to fill once again the email and / or phone number, even if the user has already filled it |  | Clarification Provided | The option to trigger notification from the Acknowledgement screen is an additional option provided, to trigger notification to additional emai ids/phone numbers. However, notification will be auto-triggered to the mobile/email id provided in the demographic page.
27 | Appointment screen | - The user can take the appointment Saturday and Sunday (need of the set up module) - If we take an appointment the 5th of May, the application shows us in the pre-registration confirmation interface the 2nd may (the pre-enrollment ID is 30630284091089) |  | Known Issue/Bug | This is a known issue - MOS-12909
28 | Appointment screen | - There is a need to access to the setup module to configure the enrollment capacity of each CSC (number of stations and the average time to enroll each person) |  | Clarification Provided | This will be provided as part of the Admin module with reference UI as part of 30Jun release.
29 | Appointment screen | - The feature of having appointment for a group of persons (family) is not available |  | Clarification Provided | MOSIP provides an option to "Add Applicant" on the Preview screen. With this feature, the user can add any number of applicants and book appointment for the group of applicants added.

## Values
Category
Known Issue/Bug
SI Customization
New Feature/Change
Clarification Provided
Need Clarity from GoM

## Attachments
S. No. | Attachment
5
6
13
22
22
24
24

## GoM_Pre-reg_Security
Pre-registration: Security Feedback from GoM - 08May'19
S.No | Technology: Category | Technology: Sub-Category | Feedback | Category | Mindtree Comments - 14May19
1 | Framework JavaScript | • Angular • Zone.js | The Zone.js and Hammer.js frameworks are not mentioned amongst the development tools in the "Architecture - DevOps Architecture V2.docs" and "Architecture - Tools and Technology Matrix_V2.xlsx" files provided by MOSIP | Clarification Provided | hammer.js and zone.js are used by angular. So, these skills are not required by the developer.
2 | JavaScript Libraries | • Hammer.js2.0.7 |  | Clarification Provided
3 | External API | • Google Font API • dev.mosip.io API | The APIs should not be external to the pre-enrollment software. We can accept that dev.mosip.io API can be independent of the pre-enrollment (but shall be deployed in the MI datacenter) However, Google fonts must be deployed within the pre-enrollment repository. MOSIP must download those fonts once for all and use them without using this API | Clarification Provided | We are looking into have the Google Font set locally so that it does not make calles to google font API over the internet
4 | Web Server | • Nginx 1.15.8 | This web server was not mentioned neither in the "Architecture - DevOps Architecture V2.docs" file or nor in the "Architecture - Tools and Technology Matrix_V2.xlsx" files provided by MOSIP, it is Tomcat which should be used according to these two files | Clarification Provided | Nginx is used as proxy server in front of the firewall. It is not used to host the application.