## MOSIP_QueryLog_External
MOSIP - Requirements Change Log
S.No. | Date of Identification | Reference (User Story/Document, Version, Section, REQ ID, Page) | Module | Change Description | Logged By | Comments
1 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Mode of login to client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint, iris. Morocco FRS: Single factor authentication using either password or OTP Query log review: Multifactor authentication using username + password and/or OTP, fingerprint, iris. Also applies to operator authentication while submitting a registration.
2 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Fingerprint capture during registration: Backlog: In scope Morocco FRS: Not in scope Query log review: In MVP
3 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Best finger detection in registration receipt: Backlog: Indicate the finger with best quality score. Morocco FRS: Not in scope. Query log review: Indicate a 1-10 ranking of fingers by quality scores.
4 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Face photograph validation during registration: Backlog: Build validation for ICAO standards. Morocco FRS: Not in scope Query log review: Build for ICAO plus one other standard.
5 | 2018-09-19 | Query log review with xxx on 19-Sep-18 - Refer <Master_Query_Log> in PwS | Registration Client | Client administration / registration / configuration: The feature is scoped but not as part of a separate application.
6 | 2018-09-19 | FRS review of Morocco FRS <Annexure D - Functional Requirement Specification dtd 15062018 [F]> | Registration Client | (Placeholder for features not covered above which are present in backlog but not in Morocco FRS) For example - Translation and transliteration, Introducer concept, End of day supervisor approval, Registration correction.
7 | 2018-10-22 | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | ID Authentication | MOSIP to have the ability to configure scenarios when individual to be notified (Through a periodic job) to update biometrics: -Child turns 5/15 -Authentication cosistently fails beyond x (configurable) times of being below the defined NFIQ threshold (configurable) Reference from Query Log: Page 42 of the RFP for SI states:"RNP may maintain a threshold for quality of biometrics and in case the quality of captured biometrics does not satisfy the threshold, the RNP may intimate the resident to update their biometrics." Does MOSIP scope include the requirement to intimate a resident to update their biometrics if quality is below threshold? As we understand, this can be triggered if a high NFIQ score is identified during authentication but the authentication fails
8 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Client | Mode of login to client, Mode of local duplicate check on client, Mode of officer authentication at end of each registration on client: Backlog: Support multifactor authentication using username + password and/or OTP, fingerprint - Iris and Face is a new inclusion as requested by GoM/PwC | Resham
9 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | CNIE Validation: 1. Inclusion of step for external system integration 2. Integration with CNIE, EC and Foreign Registration for exchange of information 3. Module with User Interface for manual validation process | Resham
10 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | CNIE Finger Print Authentication: 1. Integration with CNIE for obtaining the fingerprint data (a) in the process of demographic validation check with CNIE and (b) Biometric Update in CNIE 2. Integration of authentication solution with Fingerprint SDK 3. Decryption, Quality Analysis, Extraction and Loading features for fingerprints using the received fingerprint data from CNIE 4. Testing of the above functionalities in the five CSCs | Resham
11 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | UIN Generator: • Common NIP generator between EC and RNP • NIP generator outside IDMS • NIP generator with a density of 5% for non-guess ability • Incorporation of NIP logic (refer above) within NIP generator • APIs for integration with EC • Porting of the already generated NIPs • For those children which have been allocated NIPs by EC, the same numbers should get allocated and new numbers should not get allocated • The already generated numbers by EC should not be allocated to anyone else • Testing of integrated generator | Resham
12 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | Face De-duplication: Face ID comparison (Face deduplication) has not been considered in scope of MOSIP - Tech board to advise. - If it is required, MOSIP can provide an interface to send the photo (Maybe in bytes) as per ICAO standards. However, MT will need help from tech board on defining the face specs which can be consumed by GoM to interact with the BSP. GoM/SI will need to ensure the BSP supports face deduplication. | Resham
13 | 2018-10-24 | Discussion with GoM/PwC on 24-Oct-18 | Registration Processor | APIs: • MOSIP should provide pull APIs for printing agency • Printing agency should be able to confirm receipt of pulled information • MOSIP agency should maintain a flag and timestamp of information being pulled by printing agency | Resham

## Values
Module
Pre-registration
Registration Client
Registration Processor
ID Authentication
Kernel
Admin
resident portal, Dashboards, Reports