## Sheet1
Platform Document Components | Sub-Components | Assigned to | Current Status and ETA | % completion
1.MOSIP INTRODUCTION | 1.1 Scope | Lalana |  | 100
| 1.2 Intended Audience | Lalana |  | 100
2. MOSIP -FOR IDENTITY MANAGEMENT | 2.1 What-is an Identity Management System | Lalana |  | 100
| 2.2 Why-an Identity Management System is needed | Lalana |  | 100
| 2.3 Key Objectives of MOSIP Platform | Lalana |  | 100
3.MOSIP FUNCTIONAL OVERVIEW | 3.1 Pre-Registration | Lalana |  | 100
| 3.2 Registration Services | Lalana |  | 100
| 3.3 Registration Processor | Lalana |  | 100
| 3.4 ID Authentication | Lalana |  | 100 | LEGEND
| 3.5 Kernel | Lalana |  | 100
| 3.6 Administration | Lalana | 2019-05-31 | 0 |  | Complete
| 3.7 Resident Services | Lalana | 2019-05-31 | 0 |  | WIP
| 3.8 Partner Management | Lalana | 2019-05-31 | 0 |  | Yet to start
4. MOSIP SCOPE |  | Srijoni | Please provide a date | 0
5.Requirement Specification | 5.1 Functional Requirement Specifications | Lalana | 2019-05-31 | 60
| 5.2 Non-Functional Requirement Specifications | Lalana\Shravan | 2019-06-07 | 80
6. PRODUCT DEMO (VDs) |  | Resham\Krishnan
7.MOSIP ARCHITECTURE OVERVIEW | 7.1 Principles | Shravan |  | 100
7.2 Platform Features
| 7.2.1 Configurability | Shravan | 2019-05-31 | 90
| 7.2.2 Extensibility | Shravan | 2019-05-31 | 90
| 7.2.3 Modularity | Shravan | 2019-05-31 | 90
| 7.3 Process View | MOSIP BA |  | 100
| 7.4 Logical View | Shravan |  | 100
| 7.5 Technology Stack | Shravan |  | 100
| 7.6 Data Architecture | Shravan |  | 100
8.ARCHITECTURALLY SIGNIFICANT COMPONENTS OF MOSIP | 8.1 ID Object Definition | Shravan |  | 100
| 8.2 Configurations | Shravan |  | 100
| 8.3 Registration Packet Structure | Shravan |  | 100
| 8.4 ABIS middleware | Shravan |  | 100
| 8.5 MOSIP Biometric Data Standards | Shravan |  | 100
| 8.6 Vendor Device Specifications | Shravan |  | 100
| 8.7 Security | Shravan |  | 100
| 8.8 Core Data Management | Gurpreet |  | 100
| 8.9 Test Rig Design | Gita et al | 2019-05-31 | 40
| 8.10 Integration with External System | Sanjay Shivaji Zende | 2019-05-31 | 50
9. MOSIP APIs | 9.1 External APIs
| 9.1.1 ID Authentication APIs | Gurpreet
| 9.1.2 ABIS APIs | Sanjay Shivaji Zende
| 9.1.3 OTP Manager API | John
| 9.1.4 Pre-Registration APIs | Ravi Chitragar Balaji
| 9.1.5 Registration Processor APIs | Sanjay Shivaji Zende
9.2 Internal APIs
| 9.2.1 Kernel | John
| 9.2.2 ID Repository | Gurpreet
10.HOW TO GUIDE | 10.1 Getting Started Guide
| 10.1.1.Getting the Source Code | Ajith\Swati Raj
| 10.1.2. Setup and Configure Jenkins | Ajith\Swati Raj
| 10.1.3. Setup and Configure Jfrog | Ajith\Swati Raj
| 10.1.4. Setup and Configure SonarQube | Ajith\Swati Raj
| 10.1.5. Setup and Configure Docker Registry | Ajith\Swati Raj
| 10.1.6. Installing External Dependencies | Mohan
| 10.1.7. Configuring MOSIP | Ajith\Swati Raj
| 10.1.8. MOSIP Deployment | Ajith\Swati Raj
10.2 Developer Document
| 10.2.1.MOSIP Configuration Server | John | 2019-05-17
| 10.2.2.MOSIP REST API Guidelines | John | 2019-05-17
| 10.2.3.MOSIP Java Coding Standards | John | 2019-05-17
| 10.2.4.MOSIP Best practices of Git | John | 2019-05-17
| 10.2.5.Eclipse Markdown Editor | John | 2019-05-17
| 10.2.6.Auth Implementation | Ramadurai Pandiyan | 2019-05-17
11. INFRASTRUCTURE RECOMMENDATIONS | 11. INFRASTRUCTURE RECOMMENDATIONS | Shravan
12. GLOSSARY | 12. GLOSSARY | TBD
13. ABBREVIATIONS | 13. ABBREVIATIONS | TBD
14. REFERENCES | 14. REFERENCES | TBD
Note on A1: Windows User: As per the agreed TOC with Client