## Pre-Registration
Pre-Registration (Pre-Enrolment Application) - Section: 2.3.1
S. No. | Feature | Comments - Mindtree | Comments - Tech Board
1 | #8 - Registration - The new user should be able to register themselves by providing the mobile number and one-time pin. | GoM does not state rquirement to login with Email. Please confirm if login with EMail is also required as part of MOSIP scope? If yes, should it be considered for MVP? | Shrikant <20-Sep-18> - MVP to include email and mobile which should be configurable
2 | #12 - Appointment Change - The user should be able to change the appointment at any time no later than one day before the appointment. | It does not add value to restrict the ability to update appointment, if in any case the individual will be a no-show - In any case, this can be accommodated through configuration. | Shrikant <20-Sep-18> - OK

## Registration
Registration (Enrolment Software) - Section: 2.3.3
S. No. | Feature | Comments - Mindtree | Comments - Tech Board | Comments - Anadi <22-Oct-18>
1 | #16 - New User Registration | Requirement not clear - it states that a new user should be able to register themselves. | Shrikant <20-Sep-18> - As a security requirement, only the administrator will have the ability to register users. Self-registration is to be dis-couraged | OK
2 | #21 - Client Registration and Configuration | Client administration / registration / configuration features as part of a separate application have not been included in the MOSIP backlog - Please confirm if it is part of MVP? | Shrikant <20-Sep-18> - The feature is scoped but not as part of a separate application. Will having it as a separate software have an impact on the client software, by keeping it light - TBD with Shravan Response from Shravan: > There is no precise advantage of having a separate application for user onboarding > It only increases complexity in manageability of distributed softwares > Keeping it together enables manageability and ability to fix issues in one place > MOSIP will have a single application for registraion and user onboarding for registration client - This will be controlled based on access/role assigned | OK
3 | #22 - Administration Module | Client administration / registration / configuration features as part of a separate application have not been included in the MOSIP backlog - Please confirm if it is part of MVP?
4 | #23 - Master Data import through xml file | Master data sync is covered in MOSIP backlog but importing from a file is not considered. | Shrikant <20-Sep-18> - Considering the new xml based master data/metdata setup approach, this needs to be re-confirmed with Shravan/Anadi Response from Shravan: > MOSIP will facilitate master data exchange through a synch process > This will be a pull request from client to server > The data will be synched in Json format > It will not be an import but sync | OK
5 | #24 - User credential file import through xml file | Credential sync is covered in MOSIP backlog but importing from a file is not considered. | Shrikant <20-Sep-18> - Considering the new xml based master data/metdata setup approach, this needs to be re-confirmed with Shravan/Anadi Response from Shravan: > MOSIP will facilitate user credential exchange through a synch process > This will be a pull request from client to server > The data will be synched in Json format > It will not be an import but sync | OK
6 | #25 - Register client identity | Client administration / registration / configuration features as part of a separate application have not been included in the MOSIP backlog - Please confirm if it is part of MVP? | Shrikant <20-Sep-18> - This Requirement needs clarity, to understand if it is related to hardware mapping and difference between Enrolment kit file and Station file - Anadi | To be conveyed to PwC - Shrikant > MOSIP will use USB client and registered devices (Spec of devices yet to be finalized) > Hence, Kit concept will not be applicable
7 | #26 - Deregister Client Identity | Client administration / registration / configuration features as part of a separate application have not been included in the MOSIP backlog - Please confirm if it is part of MVP? | Shrikant <20-Sep-18> - This Requirement needs clarity, to understand if it is related to hardware mapping and difference between Enrolment kit file and Station file - Anadi | - Seek clarity from GoM/PwC - Shrikant
8 | #27 - Configure encryption and decryption certificate | Client administration / registration / configuration features as part of a separate application have not been included in the MOSIP backlog - Please confirm if it is part of MVP? | Shrikant <20-Sep-18> - This needs TBD - Anadi Response from Shravan: > MOSIP will facilitate download of Certificate but public/private keys cannot be downloaded | OK
9 | #30 - Unlock EO | MOSIP backlog only includes blacklisting of EO from Admin portal. | Shrikant <20-Sep-18> - OK. Blacklisting by admin will suffice.
10 | #37 - Demographic data capture | Additional demo fields to be captured - Address different from CNIE, Consent for sharing data. - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This needs TBD - PwC | - Seek clarity from GoM/PwC - Shrikant
11 | #56 - Packet creation and upload to be a single process. | MOSIP backlog envisages creation, export and upload to all be separate processes. - Also, need clarity on Manual process of creating enrolment Packets | Shrikant <20-Sep-18> - Keeping create, export and upload to be separate processes is how MOSIP should work. Manual creation only refers to manual upload and hence, no change in approach for MOSIP
12 | #57 - Enrolment Information Deletion - After receiving confirmation of the receipt of information by the IDMS, the packet should be marked as ‘Successfully Uploaded’. For such successfully uploaded packets, Enrolment Software should delete the uploaded enrolment packet(s) and corresponding information from local database within enrolment kit after 45 days of the enrolment. | Sending Acknowledgement is considered as PUSH Activity from Server; It is decided that it should be a pull activity from Client to read status of enrolment packets. Based on the status, the client can initiate deletion of packets | Shrikant <20-Sep-18> - OK
13 | #58 - Find my PIN - The system should have provision for finding the PIN of the applicant. For persons having age of 5 years and above, the mandatory details may include (i) Name, (ii) Gender, (iii) Date of Birth, and (iv) Biometrics. For persons below 5 years, the biometrics of parents should be captured instead of the children’s biometrics. The result of search may be provided to the applicant through SMS or Email. | New - This has not been considered considering security - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - Using the download UIN API provided by MOSIP, the SI is expected to build the customization for this purpose (Refer email dated 06-Sep-18 on RNP portal features, SUB: "Re: Urgent Clarification Needed on MOSIP")
14 | #59 - Lock and Unlock UIN | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is a MOSIP requirement Response from Shravan: > Consent management has not been considered in scope of v1 | To be included as part of v1
15 | #60 - Generate VID | Included in the resident services API package, but not in the Registration client. | Shrikant <20-Sep-18> - MOSIP will provide this as a service / API for the portal to consume. > MOSIP will implement multiple VID generation with a range within which the Country can decide the maximum limit (EG: Range of 1-5 and a Country can opt to select the number of VIDs that can be generated) > Invalidate VID on consumption of each VID > Active VID generated should be unique in the MOSIP system at any given point in time, mapped to one UIN - OK > Multiple VIDs can be mapped to one UIN > Duration of VID validity and length of VID will be configurable. | OK - To be conveyed to PwC - Shrikant
16 | #61 - Retrieve VID | New - Retrieval and replacement of VID using biometric is not considered. Ideally VID should be for immediate consumption and not for retrieval/replacement. Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - The Virtual ID(VID) is a temporary, revocable 16-digit random number mapped with the Aadhaar number. The VID can be used for the purpose of authentication in the same way the Aadhaar number is used. Currently, VID can be generated on UIDAI's resident portal - Ideally VID should be for immediate consumption and not for retrieval/replacement. Hence, retrieval and replacement of VID is not a valid requirement. | MOSIP should support this. Ability of UIN holder to retrieve all active VIDs on the web portal. To be conveyed to PwC - Shrikant
17 | #62 - Replace VID |  |  | To be conveyed to PwC - Shrikant MOSIP should support this. Ability of the UIN holder to invalidate an active VID, on the web portal. Consent management: Since id Object fields can be configured by the Country, and the consent features would depend on the id Object, implementation will be complex. Also, during run time, every auth request will have to run through additional checks based on the consent provided. Hence, this will be taken up as part of v2.

## Registration Processor
Registration Processor (Identity Management System-IDMS) - Section: 2.3.4
S. No. | Feature | Comments - Mindtree | Comments - Tech Board | Comments - Anadi <30-Oct-18>
1 | #67 - Login #68 - Security Level | Need More Clarification: - Does IDMS have a Login Portal or will it be part of Admin Portal? | Shrikant <20-Sep-18> - MOSIP to provide access control of server, to implement changes to code - Two factor authentication to be provided with UIN/biometrics and frontend Response from Shravan: > GoM to provide clarity on the purpose of login and who are the intended users? | - Seek clarity from PwC on the precise requirement, the users of this feature and the features required to be supported post login - Shrikant
2 | #71 - Initial Validation - The system should have provision to automatically send the packets for scanning through the Security Software for virus, malware, etc. - Once the packet clears the check, the system should automatically decrypt the same. - Thereafter, the contents of the received packets should get checked with Security Software for virus, malware, etc. | Need More Clarification: - Are we considering two Virus Scan in Server? - We have considered Virus Scan before Packet Upload | Shrikant <20-Sep-18> - Check with Shravan on security aspect if it adds value to perform the scan twice - Levels of scanning required should be configurable Response from Shravan: > Virus scan will be executed before passing the firewall > If ZIP file is found to be clean, it does not add value to re-scan the file again post decryption but results in wastage of processing time > This will be a fixed process (Non-configurable) | - This needs to be done at two levels since the contents of the packet are exposed only post the file is un-zipped
3 | #74 - Long Term Archival - Mark packet as ‘Received’ and provide acknowledgement to the enrolment software - Marked the packet for replication to the disaster recovery site | Need More Clarification: - Sending Acknowledgement is considered as PUSH Activity from Server; It is decided that it should be a pull activity from Client - Clarification on Disaster Recovery Site. | Shrikant <20-Sep-18> - Check with Shravan on effort of marking the packet for disaster recovery site, as this should be included - This should be included Response from Shravan: > MOSIP will archive packets post completion of packet processing > The Archival strategy as such needs to be handled by SI > SI can subsequently implement disaster recovery management | - Each implementation (Web application, web-services, vertex verticals, database) will have it’s own availability maintained. Data replication to multiple DCs and marking for disaster recovery is a deployment and infrastructure activity, which should be handled by SI. MOSIP will provide support on best practices.
4 | #75 - Structural Validation and Standardization - Validation for reference information with master data - All validation results would be stored in a validation database for purpose of reporting and other necessities - The status of enrolment should be updated appropriately in the job management database | Need More Clarification: - On Reference Info - On Validation Database - On Job Management Database - Timestamp validation | Shrikant <20-Sep-18> Explain our flow > Question to PwC - Please provide clarity on the below terms/requirement - On Reference Info - On Validation Database - On Job Management Database - Timestamp validation | OK
5 | #77 - Manual Adjudication (Quality Check) - For parent PIN update cases | Need More Clarification | Shrikant <20-Sep-18> - The relevance/inclusion of the requirement needs to be discussed with Anadi | - This scenario of updating child's UIN to update associated parent's UIN has not been considered as part of core MOSIP - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Rest can be accommodated by SI. Requirement to be further detailed by PwC vide process flow and wireframe
6 | #78 - Validation with CNIE - In case of mismatch in Date of Birth, the officer will correct the Date of Birth and resubmit the request for CNIE validation - For cases where the response is received, the system will compare the name in CNIE with the name in RNP | Need More Clarification: - Should we allow Manual Adjudicator to Update User Information - New Not in Backlog - Check for Name from CNIE | Shrikant <20-Sep-18> - The scope of this requirement needs to be discussed with Anadi (Incoming info into MOSIP and consuming the data for override and manual adjudication) | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Manual adjudication supported by MOSIP is for demographic/biometric dedupe only. Data correction can be accommodated by SI. Requirement to be further detailed by PwC vide process flow and wireframe
7 | #79 - Demographic Deduplication - An internal mapping id (VID#) with the URN number | Need More Clarification: - VID# in IDMS | Shrikant <20-Sep-18> - This can be ignored, as it refers to an iternal mapping ID for deduplication - This can be analyzed based on the demographic dedupe algorithm
8 | #80 - Check with Civil Registration | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> The scope of this requirement needs to be discussed with Anadi (Incoming info into MOSIP and consuming the data for override > manual adjudication) | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Manual adjudication supported by MOSIP is for demographic/biometric dedupe only. Data correction can be accommodated by SI. Requirement to be further detailed by PwC vide process flow and wireframe
9 | #81 - Parent / Guardian PIN and Biometric Tagging - In case the PIN is found, the PIN of parent/guardian is tagged with URN, along with the biometric of parent/guarding, request status is updated and sent to next step. - Otherwise, the request status is updated as ‘Rejected’ with appropriate reason for rejection. | Need More Clarification: - Are we not verifying the Parents Biometrics? | Shrikant <20-Sep-18> MOSIP has to perform a biometric authentication of the parent with the data available in system, prior to allocating the UIN - Re-confirm with Anadi | - MOSIP should continue with the identified approach of verifying the parent's/guardian's UIN and authenticating the biometrics - To be conveyed to PwC - Shrikant
10 | #83 - PIN Generation or Allocation For cases of children below 5 years of age to whom PIN has already been allotted by Civil Registration System, the same PIN is allocated. | Need More Clarification: - PIN for Civil Registration System and PIN for MOSIP are Same? | Shrikant <20-Sep-18> - PINs generated for children in Civil Registration System should be consumed for a child and not issue a new UIN - MOSIP to ensure MOSIP does not issue existing set of UINs - MOSIP to receive a set of existing PINs from Civil registry which should be blacklisted in MOSIP
11 | #80 - Super User Creation - SetUp | Need More Clarification: - Role of Super User and Differnet Users in IDMS as it is Server. | Shrikant <20-Sep-18> The relevance/inclusion of the requirement needs to be discussed with Anadi | - Need clarity from PwC on IDMS Org. structure - Shrikant
12 | #85 - Setup of enrolment officers - The system should have a provision for enrolment officer to apply to the web portal with role as an EO. | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - MOSIP to analyze if user onboarding can be done through a portal, as in any case client needs to be online for initial user onboarding - MT team/Shravan to analyze and provide inputs - Shrikant/Anadi to provide feedback Response from Shravan: > This has not been considered in scope - Requirement to be detailed/MVP/Non-MVP? | - Setup of RO through an RO applying through a web portal, workflow management, linking to Partner Management is not a secure practice and not part of MOSIP scope - This needs conveyed to PwC - Shrikant
13 | #86 - Setup of CRM users and administrators | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - MOSIP should provide access to the system - Setup of CRM users - Check with Anadi | - Setup of external system users is not in MOSIP scope - MOSIP will provide an interface to external systems to access MOSIP data through event mechanism - This needs conveyed to PwC - Shrikant
14 | #87 - Setup of KMS administrators and users | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP?
15 | #88 - Setup of BI and Analytics users | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP?
16 | #89 - Setup of Partner Management Users | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? What is the relevance of having users for IDMS?
17 | #90 - Setup of DMS users | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP?
18 | #91 - Setup of DBA , Middleware admins and Server Administrators | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? Please specify the roles DBA and Server Admin. | Shrikant <20-Sep-18> - Setup of DBA, Middleware admins and Server Administrators - Check with Anadi | - This can be handled by SI

## ID-Authentication
ID-Authentication (Authentication Solution) - Section: 2.3.5
S. No. | Feature | Comments - Mindtree | Comments - Tech Board | Comments - Anadi <30-Oct-18>
1 | #97 - Super Administrator | Need more Clarity on why it is under IDA | Shrikant <20-Sep-18> - To be checked with PwC
2 | #98- Login | Need more Clarity on why it is under IDA | Shrikant <20-Sep-18> - This refers to admin login for auth based configs
3 | #99- Security Level | Not clear on the Requirement | Shrikant <20-Sep-18> - This refers to admin login security for auth based configs
4 | #100- Creation of users of authority officials | Need more Clarity on why it is under IDA | Shrikant <20-Sep-18> - This refers to user creation and hierarchy
5 | #101- Activation or Deactivation of authority users | Need more Clarity on why it is under IDA | Shrikant <20-Sep-18> - This refers to activating/deactivating users/TSPs
6 | #111-Record Creation in Auth Server - Synchronization and retrieval of fingerprint minutiae from CNIE Fingerprint Library (in case of Approach-II) | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - The scope of the requirement needs to be discussed with Anadi/GoM | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Extraction of fingerprint minutiae and passing on the minutiae to MOSIP can be accommodated by SI. Requirement (Push/Pull mechanism) to be further detailed by PwC vide process flow
7 | #112 - Demographic Update - This should include any update in CNIE number pursuing to renewal of CNIE by resident. | Please elaborate requirement. | Shrikant <20-Sep-18> - The scope of the requirement needs to be discussed with Anadi | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Update of CNIE data to be updated in MOSIP should be accommodated by SI, through a correction packet received from CNIE. Requirement (Push/Pull mechanism) to be further detailed by PwC vide process flow
8 | #114 - Record Suspension - The administrator should be able to suspend the PIN for authentication with clear reasons, suspension duration and indicate corrective action to be taken by resident, if any | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - The scope of the requirement needs to be discussed with Anadi | This feature of suspending UIN for authentication is not to be supported by MOSIP but can be implemented by SI. MOSIP will support maintenance of default states – Active and Inactive. MOSIP will facilitate configuration of states, to facilitate inclusion of new state/change of current state. (Active – Suspended for Auth)
9 | #115 - Record Deactivation - On registration of death of resident, the resident’s record should be marked as deactivated. | Relevance of requirement and repurcussions TBD | Shrikant <20-Sep-18> - The policy/scope of the requirement needs to be discussed with Anadi > PoR/Death certificate with UIN/biometrics > Send to manual adjudicator vs. not allowing deactivation | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Request to deactivate the UIN in MOSIP should be accommodated by SI, through a correction packet received through the data enrichment API. Requirement (Push/Pull mechanism) to be further detailed by PwC vide process flow
10 | #116- Receipt of Request in XML | Request in XML/JSON should be decided by tech board | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - This should be in JSON format in MOSIP - SI can transmit to XML/other formats as required
11 | #117- Automatic Routing of Request | Multiple DC Implementation is considered as part of design. The logic of routing is a deployment configuration, to be carried out by SI. | Shrikant <20-Sep-18> - Multiple DC Implementation is considered as part of design. The logic of routing is a deployment configuration, to be carried out by SI.
12 | #120 - Structural Validation - The system should be able to XML / JSON structural compliance check | Request in XML/JSON should be decided by tech board | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - This should be in JSON format in MOSIP - SI can transmit to XML/other formats as required
13 | #121 124 - TSP Signature /Code Validation | Not clear on the Requirement - Does TSP Code refer to the TSP ID here? | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - Clarified and discussed during process flow walk-through on 02-Nov-18
14 | #122 125 - UA Signature/Code Validation | Not clear on the Requirement - Does UA Code refer to the UA ID here? | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - Clarified and discussed during process flow walk-through on 02-Nov-18
15 | #126 - Registered Device Code Validation - The system should be able to validate the registered device code | Does this indicate all TSP devices for a Country should be registered? | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - All registration, authentication, TSP devices should be registered in MOSIP eco-system
16 | #128 -Status Check for PIN | New - Biometric Lock For PIN/UIN status check - Does this refer to validating if the PIN is a valid one and is active? | Shrikant <20-Sep-18> - This refers to valiadting if UIN is active or any other status
17 | #134-Fingerprint Authentication In case of Approach-I, the system should be able to send request to CNIE and receive the response. In case of Approach-II, the system should be able to retrieve the CNIE number and corresponding fingerprint minutiae from CNIE Fingerprint Library hosted in RNP Data Centre. Thereafter, the system should use the Fingerprint SDK to perform matching the Fingerprint in request with Fingerprint in resident data store using the Fingerprint SDK. | New – Not in Backlog – Approach I and Approach II | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - MOSIP will provide an interface as part of of the External Data Enrichment Module/API. Extraction of fingerprint minutiae and passing on the minutiae to MOSIP can be accommodated by SI during registration processing, which can be stored in auth server. Requirement (Push/Pull mechanism) to be further detailed by PwC vide process flow
18 | #136-Fraud Check | New – Not in Backlog | Shrikant <20-Sep-18> - This is not considered in MOSIP and is SI scope
19 | #139-Response Preparation in XML | Response in XML/JSON should be decided by tech board | Shrikant <20-Sep-18> - This needs to be discussed with Anadi | - This should be in JSON format in MOSIP - SI can transmit to XML/other formats as required
20 | #144-147-Reporting | New - Not in Backlog > MOSIP will provide an interface to external reporting system(s) to access the required data - To be confirmed | Shrikant <20-Sep-18> - This is not considered in MOSIP and is SI scope

## Partner & Device Management
Partner & Device Management - Section: 2.3.6
S. No. | Feature | Comments - Mindtree | Comments - Tech Board | Comments - Anadi <30-Oct-18>
1 | #153 - Setup Enrolment Agency: DOA should be able to enter the details of Enrolment Agency on the ‘Enrolment Partner Management Module’ of RNP portal. A unique 2-digit code (hereafter referred to as EA Code) should be allocated to the EA | The concept of Enrolment agency is not yet considered in the MOSIP backlog | Shrikant <20-Sep-18> - MOSIP should consider mapping of Registrar Agency with Registration Centre (RC mapped to two levels of agency/cross mapping > Agency working with multiple registrars and vice-versa but - Operator can be assigned to RA/Registrar) - This should be configurable - TBD with Shravan and included in product backlog Response from Shravan: > This concept of two-level mapping has not been considered in scope > TBD with Anadi | - This should be considered as part of MOSIP scope to facilitate control and lifecycle management of Registrars. Open-source LDAP should facilitate definition of Organization Structure and SI can implement accordingly.
2 | #154 - Activation or Deactivation of Enrolment Agency: DOA should be able to activate and deactivate the Enrolment Agency for a given time period or on permanent basis
3 | #155 - Administrative User Creation for EA : DOA should be able to create one administrative users for the Enrolment Agency. For creation of user, the details such as PIN, Mobile Number may be entered. Hereafter, this user is being referred to as Enrolment Agency Administrator (EAA)
4 | #156 - Activation or Deactivation of Administration Users for Enrolment Agency: DOA should be able to activate or deactivate its EOs for a given time period or on permanent basis. This will be subject to any restrictions put in place by the Authority
5 | #160 - Naming of Enrolment Kit: The identity of enrolment kit should be allocated by Asset Management Tool. EAA should be able to allocate a name to each enrolment kit. The name should be a 5-digit number which will be preceded by EA Code making it unique. This 5-digit number should be unique amongst enrolment kits of respective EA. For each enrolment kit, the MAC address (hereafter referred to as ‘enrolment kit identity’) should also form part of the enrolment kits details. | The concept of Registration Kit is not yet considered in the MOSIP backlog. Please elaborate the specifics of Registration Kit. | Shrikant <20-Sep-18> - Registration Kit - Refers to all device types, device ID (MAC ID), S.no. - Naming of Registration Kit and customization of kits should be part of SI scope along with activation/deactivation,dates, download of EA kit etc - Concept of Registration Kit to be elaborated - MOSIP to recommend generic solution to provide a Registration Kit | This needs to be conveyed to PwC - Shrikant > MOSIP will use USB client and registered devices (Spec of devices yet to be finalized) > Hence, Kit concept will not be applicable
6 | #161 - EAA should be able to setup a start date and end date for enrolment kit
7 | #162 - Activation and Deactivation of Enrolment Kit : EAA should be able to setup a activate and deactivate for enrolment kit for a given time period or on permanent basis
8 | #163 - DOA should be able to deactivate any enrolment kit
9 | #187 - Enrolment Kit Identity - EAA should be able to download the enrolment kit identity list in the form of .zip file contain an digitally signed .xml file
10 | #164 - Configuration of Enrolment Packet Creation and Upload | Need clarification on Manual process of creating enrolment Packets | Shrikant <20-Sep-18> - This refers to manual upload of packets. Hence, no change in approach as designed by MOSIP
11 | #167 - Application Form Submission: The candidates wishing to become Enrolment Officer should be able to apply in the portal. For this purpose, they can register using their PINs. | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope. - MOSIP to provide product documentation support. | This needs to be conveyed to PwC - Shrikant
12 | #168 - Application Form Scrutiny: DOA (or representative of agency deputed by the Authority), should be able to scrutinize and accept or decline (with reasons) the applications
13 | #169 - Schedule of Training and Examination : DOA (or representative of agency deputed by the Authority), should be able to schedule the training and examination
14 | #170 - Approval of Candidates : The system should have facility for DOA to approve the registered candidates
15 | #171 - Selection of Training Schedule: The registered candidates who have been approved, should be able to see the forthcoming trainings and should be able to select any one session
16 | #172 - Training Attendance: DOA (or representative of agency deputed by the Authority), should be able to mark attendance of all candidates present for the trainin
17 | #173 - Selection of Examination Schedule : The candidates which have attended training should be able to select any examination date and location
18 | #174 - Result of Examination : DOA (or representative of agency deputed by the Authority), should be able to schedule the attendance and result of examination. The result of examination should include the identification of candidate as ‘Operator’ depending on the marks obtained in examination.
19 | #175 - Intimation of Examination Result : The system should be able to intimate the result of examination to the candidate using SMS and Email
20 | #176 - Process for Failed Candidates : For the candidates absent or failed in the examination, the application process should allow to re-attend training, reappear for examination and pass the examination. The system should be able to support this cycle for up to a maximum of 5 attempts.
21 | #180 - EAA should be able to setup a start date and end date for EOs | New - This has not been considered. This will result in running a job to automatcially de-activate Eos on the end date - Please confirm if it is part of MOSIP scope/MVP? MOSIP backlog includes: - Marking EO as active/inactive/blacklist/un-blacklist - Marking EC as active/inactive | Shrikant <20-Sep-18> - MOSIP should should be able to setup a start date and end date for ROs - TBD with Shravan and added to PB, as new requirement Response from Shravan: - This can be included - Added to MOSIP backlog | OK
22 | #188 - Reporting of Candidates - DOA should be able to see the list of candidates with respective stages of their training and examination process. In the drill down, the system should show details of one candidate. | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope. | This needs to be conveyed to PwC - Shrikant
23 | #189 - Reporting of Candidates - DOA should be able to see the list of candidates, who applied for training and examination along with the summary of results, if available
24 | #194 - Downloads : Enrolment Software | Should MOSIP allow the download of latest enrolment software publicily? | Shrikant <20-Sep-18> - MOSIP should support download, but only on dongle and not on the hard disk/OS of the user - TBD with Shravan Response from Shravan: - MOSIP will support donwload on dongle - Read only software | OK
25 | #195 - Training Curriculum and Material | Assuming that Mindtree will provide the material but it will be on the portal which will not be hosted by Mindtree. | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope - MOSIP to provide product documentation support | This needs to be conveyed to PwC - Shrikant
26 | #199 - TSP Creation - All the required documents, procedures and eligibility criteria for on boarding of TSP and UAs should be available on the public portal. | Assuming that Mindtree will provide the material but it will be on the portal which will not be hosted by Mindtree. | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope - MOSIP to provide product documentation support | This needs to be conveyed to PwC - Shrikant
27 | #200 - TSP Approval authority management: Application should have capability to create, modify and drop administration rights of TSP. TSP admins should be able to manage the lifecycle management of approval authority for TSP/UA creation | New - Approval Authority - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope - MOSIP to provide product documentation support | This needs to be conveyed to PwC - Shrikant
28 | #201 - Workflow Management : Application should be able to create workflows. Approval authority should be able to fill in observations before on boarding TSPs by carrying out audits, upload any audit/assessment checklists etc., any documentary evidences etc., to the application and approve, reject workflow requests during TSP approval process. | New - Workflow Management - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope - MOSIP to provide product documentation support | This needs to be conveyed to PwC - Shrikant
29 | #205 - UA Admin Management : Application should allow creation of UA administrator for allowing TSP to create new UA agencies. | On TSP and UA - MOSIP has considered AUA and ASA as TSPs which can be hierarchial. | Shrikant <20-Sep-18> - MOSIP to use terminology and hierarchy of MUA/MSA - This refers to creation of TSP admin by super admin
30 | #206 - UA Creation : Application should allow creation of UA agencies. UA admins would be able to start the on-boarding of UA by capturing details of UA in the application. Interested parties would be able to download UA form on the RNP public portal and send the form along with required documents to UA admin mail. UA admin would capture these details on UA GUI to start a workflow. These workflows would need the approval authority to complete any verification/audit process, fill in the required compliance checks and approve the creation. Application would create the UA in the system including the UA credentials/license keys etc | Additional Section Requested – Scope Increase – MOSIP Admin would do this | Shrikant <20-Sep-18> - This is not MOSIP scope. This is to be considered as SI scope as part of public portal. | This needs to be conveyed to PwC - Shrikant
31 | #207 - Entry of Certified Devices : The designated officials of authority (DOA) i.e. users which will act on behalf of the authority to create an entry of certified devices i.e. their make, model, type (iris), certificate number, date of certification, certification end date, etc. | What is the difference between Certified Device and Registered Device | Shrikant <20-Sep-18> - Certified devices: Particular model of particular devices which go through a quality test. MOSIP will store the device spec (Model, Make, Type) of certified devices - Registered devices: Devices with specific set of serial number as registered (As under "Type")
32 | #208 - Renewal of Certified Devices : The designated officials of authority (DOA) will be able to mark the renewal of existing certified devices by selecting make, model, type (iris) of concerned device and entering renewal details such as certificate number, date of certification, certification end date | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? ( Certified Device vs Registered Device) | Shrikant <20-Sep-18> This needs to be considered - Certification date of validation, valid until etc
33 | #209 - Suspension of Certified Devices : The designated officials of authority (DOA) will be able to suspend the certified devices by selecting make, model, type (iris) and entering the suspension order number and effective date till which suspension should be valid. | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? ( Certified Device vs Registered Device) | Shrikant <20-Sep-18> This needs to be considered - Certification date of validation, valid until etc
34 | #210 - Revocation of Suspension: The suspension of the certified device should be revocable under two circumstances (i) Automatically on expiry of suspension period, (ii) Manually revoking the suspension by selecting make, model, type (iris) and entering the suspension revocation order number and effective date till which revocation is valid | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? ( Certified Device vs Registered Device) | Shrikant <20-Sep-18> This needs to be considered - Certification date of validation, valid until etc
35 | #213 - Registration of Devices by residents: This functionality is similar to that of ‘Registration of Devices by UAs’. The resident would be required to login using PIN and OTP in the portal. At the time of suspension of certified device, any new device of the concerned make and model should not be allowed to get registered. | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? Need elaboration on requirement. | Shrikant <20-Sep-18> - Need clarity from Anadi/GoM | This needs to be conveyed to PwC - Shrikant > Resident is the end user and not required to carry out authentication and hence, this requirement is not considered as part of MOSIP scope
36 | #214 - Deregistration of device by residents : This functionality is similar to that of ‘Deregistration of Devices by UAs’. The resident would be required to login using PIN and OTP in the portal.
37 | #215 - Key Creation/Renewal : On the expiry of existing keys or request for new keys, the solution should be able to generate the keys for the following: 1. Private and Public Key for RNP-DS 2. Private and Public Key for TSPs 3. Private and Public Key for UAs HSM will have functionalities of overall key management (creation, access, archival, destruction). | Need more clarity on UA and RNP-DS | Shrikant <20-Sep-18> - TBD with Anadi | - Data Store should be encrypted with keys
38 | #216 - Key Access : The user should be able to access the relevant keys: 1. Private Keys for RNP-DS: RNP Administrators 2. Private Key for TSPs: TSPs 3. Private Keys for UAs: UAs 4. Public Key for RNP-DS: RNP Administrator 5. Public Key for TSPs: RNP Administrator and TSP 6. Public Key for UAs: RNP Administrator, TSP and UA
39 | #217 - Key Archival and Destruction The user should be able to archive and destruct the keys | MOSIP has considered invaldiating keys post its validity period, subsequent to which, the key should be requested again and allocated. | Shrikant <20-Sep-18> - TBD with Anadi | - Keys don't need to be archived but replaced with a new one once expired - Supported through Key rotation in MOSIP

## Support Applications
Support Applications - Section: 2.4
S. No. | Module | Feature | Comments - Mindtree | Comments - Tech Board | Comments - Anadi <30-Oct-18>
1 | Web Portal | 2.4.1.3 - RNP Public Portal Module | New - This is Not in scope for MOSIP. This is RNP PUBLIC portal The static content (information) would not be inscope of MOSIP. MOSIP would provide pre-enrolment interface and enrolment client. Pre enrolment client would be exposed as an API. Reference implementation would be provided. Dashboards and reports would be created by SI. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
2 | Web Portal | 2.4.1.4 - RNP Private Portal Module | New - Private portal is not a part of MOSIP scope. MOSIP will provide the base features which need to be consumed by the portal. For example, MOSIP will provide reference implementation of admin screens and manual adjudication screens, which can be implemented in the portal Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
3 | Web Portal | 2.4.1.5 - Resident Services Module | MOSIP will provide API to access services like “nearest enrolment center”, “download id” We have referred to resident.uid.gov.in and only relevant backend API for the same would be provided Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
4 | Web Portal | Sec: 2.4.1.5 #249 Language - The portal should be viewed in Arabic, and French | Frontend for Arabic and French would be created by SI. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
5 | Web Portal | Sec: 2.4.1.5 #251 - Enrolment Centres information - Portal should have a page to search on the enrolment centres available in an area and result should show map, directions, address, and contact numbers of the centre. | Considered as part of Pre-Enrolment reference implementation. Exposed as API if it needs to be consumed separately | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
6 | Web Portal | Sec: 2.4.1.5 #253 - PIN Status - The resident should be able to check his PIN status post enrolment. Status of enrolment would be updated on the web page using an open API that would be available for status check. Resident would be able to check status using an ERN number. | Tracking UIN generation has been considered. Assuming PIN is the unique ID number (UIN) that is generated, same as Aadhaar for India | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
7 | Web Portal | Sec: 2.4.1.5 #255 - Get PIN on mobile - This web page should allow a resident to receive PIN on mobile number and OTP authentication. The system should search the identity repository for given mobile number, In case the mobile number exists in the record for some PIN as a registered mobile number, an OTP should be sent to the mobile number for authentication. The resident would enter his mobile number on the screen followed by an OTP based authentication. Successful authentication would allow the PIN to be received as an SMS on the registered mobile number. | As per tech board, this may lead to privacy violation. Not recommended for MOSIP feature. SI can consider building as a local customization. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
8 | Web Portal | Sec: 2.4.1.5 #256 - Retrieve Lost ERN - This web page should allow the resident to retrieve lost ERN by entering the demographic details such as Name, Gender, Date of Birth and Mobile Number. For residents above 18 years, the CNIE number may also be asked | Only retrieval of Lost UIN is considered, which needs to be de-scoped considering the feedback for #257 | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
9 | Web Portal | Sec: 2.4.1.5 #257 - Retrieve Lost PIN - This web page should allow the resident to retrieve lost PIN by entering the demographic details such as ERN (optional), Name, Gender, Date of Birth and Mobile Number. For residents above 18 years, the CNIE number may also be asked. In case the details match, the resident should | As per tech board, this may lead to privacy violation. Not recommended for MOSIP feature. SI can consider building as a local customization. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
10 | Web Portal | Sec: 2.4.1.5 #259 - Verify PIN - The system should allow anyone to enter the PIN number for which the details are required. The system should ask for the mobile number of the requestor and sent an OTP. Upon receiving the OTP, the system should be able to show basic details such as:  Gender  Broad Age Group (e.g. 30 – 40 years)  Region or Province The exact details to be displayed after OTP verification may be decided at the time of implementation | As a process, this is similar to download UIN. However, this has not been considered. The Download UIN service will need to be customized by the SI to suit their local requirements. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
11 | Web Portal | Sec: 2.4.1.5 #260 - Verify Mobile /Email Address - The system should allow anyone to enter the PIN number for which the mobile number and email address are to be verified. The system should ask for the PIN and show masked Mobile Number and Email Address. Alternatively, the system should ask resident to enter the mobile number and/or email address and verify whether the details match its record or not. | MOSIP is providing a demographic Auth service. This requirement is partially covered with demographic Auth, the rest SI will have to customize. Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant
12 | Web Portal | Sec: 2.4.1.5 #261 - Lock /Unlock Biometrics | This has not been considered as part of the current backlog (Consent Management) but can be included considering privacy. - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This needs to be considered - TBD with Shravan Response from Shravan: > Consent management has not been considered in scope of v1 | This needs to be conveyed to PwC - Shrikant > Since id Object fields can be configured by the Country, and the consent features would depend on the id Object, implementation will be complex. Also, during run time, every auth request will have to run through additional checks based on the consent provided. Hence, this will be taken up as part of v2.
13 | Web Portal | Sec: 2.4.1.5 #262 - PIN Authentication History - For any record in history, system should permit the resident to raise grievance to the authority. | The grievance part is not considered - Please confirm above | Shrikant <20-Sep-18> - MOSIP to provide access to CRM system into MOSIP data for grievance management - TBD with Shravan Response from Shravan: > MOSIP will provide auth history which can be accessed consuming the auth history API | This needs to be conveyed to PwC - Shrikant > MOSIP will provide auth history which can be accessed consuming the auth history API
14 | Web Portal | Sec: 2.4.1.5 #263 - Grievance Logging and Status - The portal should direct the user to the CRM application where these functionalities should be available. | MOSIP will provide an interface to access MOSIP DB - Please confirm above | Shrikant <20-Sep-18> - OK | This needs to be conveyed to PwC - Shrikant > MOSIP will provide an interface to access MOSIP DB
15 | Document Management System | 2.4.2 - Document Management System | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is can be carried out by SI - Not in MOSIP scope | This needs to be conveyed to PwC - Shrikant > This is can be carried out by SI - Not in MOSIP scope
16 | Knowledge Management System | 2.4.3 - Knowledge Management System | New - This has not been considered. (MOSIP will provide training material only) - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is can be carried out by SI - Not in MOSIP scope | This needs to be conveyed to PwC - Shrikant > This is can be carried out by SI - Not in MOSIP scope
17 | Business Intelligence and Analytics | 2.4.4 - Business Intelligence and Analytics | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is can be carried out by SI - Not in MOSIP scope | This needs to be conveyed to PwC - Shrikant > This is can be carried out by SI - Not in MOSIP scope
18 | Customer Relationship Management | 2.4.5 - Customer Relationship Management | New - This has not been considered - Please confirm if it is part of MOSIP scope/MVP? | Shrikant <20-Sep-18> - This is can be carried out by SI - Not in MOSIP scope | This needs to be conveyed to PwC - Shrikant > This is can be carried out by SI - Not in MOSIP scope
19 | TSP Application | 2.4.6 - TSP Application | New - TSP Application/frontend is not a part of MOSIP scope. MOSIP will provide the base features which need to be consumed by the TSP. For example, MOSIP will provide the APIs which will enable system to receive request from AUA for authentication Frontend if required can be created by SI. Please confirm above | Shrikant <20-Sep-18> - TBD with Anadi | This needs to be conveyed to PwC - Shrikant > TSP Application/frontend is not a part of MOSIP scope. MOSIP will provide the base features which need to be consumed by the TSP. For example, MOSIP will provide the APIs which will enable system to receive request from AUA for authentication Frontend if required can be created by SI.
20 | UA Application | 2.4.7 - UA Application | New - UA Application/frontend is not a part of MOSIP scope. MOSIP will provide the base features which need to be consumed by the UA. For example, MOSIP will provide the APIs which will enable system to send request to TSP for authentication Frontend if required can be created by SI. Please confirm above | Shrikant <20-Sep-18> - TBD with Anadi | This needs to be conveyed to PwC - Shrikant > UA Application/frontend is not a part of MOSIP scope. MOSIP will provide the base features which need to be consumed by the UA. For example, MOSIP will provide the APIs which will enable system to send request to TSP for authentication Frontend if required can be created by SI.

## MISC
Values
Web Portal
Document Management System
Knowledge Management System
Business Intelligence and Analytics
Customer Relationship Management
TSP Application
UA Application